## Slide 1: Team Ink3D Status 4/25/14
Daniel Lain
Tim Edmonson
Shawn Simonson
Jesse Bowles

## Slide 2: Project Status
Task Number | Task Name | Planned Start | Planned Finish | Planned Work Hours | Actual Work Hours | % Work Completed | Earned Vaule
2 | Senior Design 2 | Wed 1/15/14 | Fri 5/23/14 | 762 | 307 | 33.07 | 252
2.1 | Documents | Wed 1/15/14 | Fri 5/23/14 | 242 | 256 | 100 | 242
2.1.1 | Detailed Design Documnetation | Tue 1/21/14 | Fri 2/28/14 | 142 | 212 | 100 | 142
2.1.1.1 | Version 1.0 | Tue 1/21/14 | Thu 2/20/14 | 72 | 208 | 100 | 72
2.1.1.2 | Version 2.0 | Wed 2/12/14 | Fri 2/28/14 | 70 | 4 | 100 | 70
2.1.2 | Test Plan | Thu 2/20/14 | Tue 3/18/14 | 100 | 44 | 100 | 100
2.2 | Prototype Implementation | Tue 2/18/14 | Thu 5/15/14 | 500 | 46 | 0 | 0
2.2.1 | Version 0.0 | Tue 3/18/14 | Tue 4/1/14 | 100 | 46 | 0 | 0
2.2.2 | Version 0.5 | Tue 3/4/14 | Tue 3/18/14 | 100 | 0 | 0 | 0
2.2.3 | Version 1.0 | Tue 3/18/14 | Tue 4/1/14 | 100 | 0 | 0 | 0
2.2.4 | Version 2.0 | Tue 4/1/14 | Tue 4/15/14 | 100 | 0 | 0 | 0
2.2.5 | Final Product | Tue 4/15/14 | Tue 4/29/14 | 100 | 0 | 0 | 0
2.3 | Final Documetation | Tue 4/1/14 | Tue 4/29/14 | 10 | 0 | 0 | 0
2.4 | Architecture Design Version 2.1 | Tue 1/21/14 | Mon 2/24/14 | 10 | 5 | 100 | 10
3 | Presentations | Fri 9/13/13 | Fri 4/25/14 | 49 | 49 | 89.8 | 44
3.4 | Detailed Design Review | Thu 2/20/14 | Tue 2/25/14 | 7 | 18 | 100 | 7
3.6 | Team Stauts Report SD2 | Thu 1/23/14 | Fri 4/25/14 | 8 | 4 | 37.5 | 3
4 | Team Meetings | Tue 9/10/13 | Tue 12/9/14 | 496 | 209 | 83.87 | 416
4.2 | Team Meeting SD2 | Tue 1/14/14 | Thu 5/1/14 | 272 | 101 | 70.59 | 192
5 | Sponser Meetings | Mon 9/9/13 | Tue 9/9/14 | 30 | 20 | 0 | 0
6 | MS Project | Sun 9/29/13 | Thu 10/23/14 | 40 | 30 | 50 | 20
6.2 | SD 2 | Thu 1/23/14 | Thu 1/23/14 | 20 | 8 | 0 | 0

## Slide 3: Testing
Junit Tests Completed
  DB
  Preprocessing
  Processing
  Post Processing
Needs Tests
  UI Controllers
  Printer Feedback Layer
  Communications Layer
  Feedback Layer

## Slide 4: GUI and Controllers
Implemented
  Print Job GUI
  Printer
  Material
  Import
Issues
  Minor Bug fixes
  Needs Junit tests

## Slide 5: GUIs and Controllers
Completed
  Modularized Main GUI
  Print GUI/Controller
  Extruder GUI/Controller
In Progress
  Automated Unit Tests
  Status GUI/Controller
    Issues testing based on communications layers.

## Slide 6: Processing Layers
Modifications
  Tool change codes
  Absolute vs. Percentage values
  ME team post processing scripts

## Slide 7: Communications Layer Status
Currently testing finalized version with printer.
In Progress. Estimated finish Monday (04/28)

## Slide 8: Testing Problems
Integrated version does not work.
Threading issues (is jSSC thread safe)?
Stand alone test (not threaded) is fully operational.
Fallback: non-threaded communications layer.
Consequence: May make the UI less responsive.

## Slide 9: Communications: Looking Forward
Several opportunities for printer access.
Complete testing using fallback only if absolutely necessary.

## Slide 10: Next Steps
Finish Stage Three
  Integration
  Testing
  Polishing
Prepare Final Documents