## Slide 1: Team Ink3D Status 2/28/14
Daniel Lain
Tim Edmonson
Shawn Simonson
Jesse Bowles

## Slide 2: Project Status
Task Number | Task Name | Planned Start | Planned Finish | Planned Work Hours | Actual Work Hours | % Work Completed | Earned Vaule
2 | Senior Design 2 | Wed 1/15/14 | Fri 5/23/14 | 762 | 223 | 19.95 | 152
2.1 | Documents | Wed 1/15/14 | Fri 5/23/14 | 242 | 218 | 58.68 | 142
2.1.1 | Detailed Design Documnetation | Tue 1/21/14 | Fri 2/28/14 | 142 | 212 | 100 | 142
2.1.1.1 | Version 1.0 | Tue 1/21/14 | Thu 2/20/14 | 72 | 208 | 100 | 72
2.1.1.2 | Version 2.0 | Wed 2/12/14 | Fri 2/28/14 | 70 | 4 | 100 | 70
2.1.2 | Test Plan | Thu 2/20/14 | Tue 3/18/14 | 100 | 6 | 0 | 0
2.2 | Prototype Implementation | Tue 2/18/14 | Thu 5/15/14 | 500 | 0 | 0 | 0
2.2.1 | Version 0.0 | Tue 2/18/14 | Tue 3/4/14 | 100 | 0 | 0 | 0
2.2.2 | Version 1.0 | Tue 3/4/14 | Tue 3/18/14 | 100 | 0 | 0 | 0
2.2.3 | Version 2.0 | Tue 3/18/14 | Tue 4/1/14 | 100 | 0 | 0 | 0
2.2.4 | Version 3.0 | Tue 4/1/14 | Tue 4/15/14 | 100 | 0 | 0 | 0
2.2.5 | Final Product | Tue 4/15/14 | Tue 4/29/14 | 100 | 0 | 0 | 0
2.3 | Final Documetation | Tue 4/1/14 | Tue 4/29/14 | 10 | 0 | 0 | 0
2.4 | Architecture Design Version 2.1 | Tue 1/21/14 | Mon 2/24/14 | 10 | 5 | 100 | 10
3 | Presentations | Fri 9/13/13 | Fri 4/25/14 | 49 | 48 | 89.8 | 44
3.4 | Detailed Design Review | Thu 2/20/14 | Tue 2/25/14 | 7 | 18 | 100 | 7
3.6 | Team Stauts Report SD2 | Thu 1/23/14 | Fri 4/25/14 | 8 | 3 | 37.5 | 3
4 | Team Meetings | Tue 9/10/13 | Tue 12/9/14 | 496 | 181 | 70.97 | 352
4.2 | Team Meeting SD2 | Tue 1/14/14 | Thu 5/1/14 | 272 | 73 | 47.06 | 128
5 | Sponser Meetings | Mon 9/9/13 | Tue 9/9/14 | 30 | 20 | 0 | 0
6 | MS Project | Sun 9/29/13 | Thu 10/23/14 | 40 | 28 | 50 | 20
6.2 | SD 2 | Thu 1/23/14 | Thu 1/23/14 | 20 | 6 | 0 | 0

## Slide 3: Traceability Analysis
Coupling / Cohesion
  GUI – Controller – Data
  Data – Processing
  Preprocessing – Processing – Post Processing
Independence
Critical Modules
  Preprocessing
  Processing
  Post-Processing

## Slide 4: Q: Are you going to help the user navigate the configuration?
User Manual
Knowledgeable Client
The design is from their input
Help menu isn’t necessary

## Slide 5: Relationship between object complexity and performance
More complex objects or objects that are split into many subsections will take longer to process
Performance is not an issue for customer
Unification Module Responsibilities
Simply responsible for putting G-Codes for each subsection together
Starts from the lowest subsection

## Slide 6: Q: Are there any specific hardware components/characteristics that affect the design of your software?
Abstraction: The communications layer is the only layer that deals directly with hardware. The subsystems are developed in such a way that core functionality can be abstracted away (interfaces).
Input/Output remain unchanged and well defined. The black box (implementation) changes to reflect the hardware.
The concrete implementation that we develop for their firmware is specific to that firmware (Marlin/RepRap)s