## Slide 1: Team Ink3D Status 1/24/14
Daniel Lain
Tim Edmonson
Shawn Simonson
Jesse Bowles

## Slide 2
Task Number | Task Name | Planned Start | Planned Finish | Planned Work Hours | Actual Work Hours | % Work Completed
1 | Senior Design 1 | Fri 1/18/13 | Tue 12/9/14 | 327 | 202 | 100
1.1.3.3 | ADS Version 2.0 | Fri 1/18/13 | Mon 1/20/14 | 30 | 12.5 | 100
2 | Senior Design 2 | Wed 1/15/14 | Fri 5/23/14 | 752 | 3 | 0
2.1 | Documents | Wed 1/15/14 | Fri 5/23/14 | 242 | 3 | 0
2.1.1 | Detailed Design Documnetation | Wed 1/15/14 | Tue 2/18/14 | 142 | 3 | 0
2.1.1.1 | Version 0.0 | Wed 1/15/14 | Tue 2/11/14 | 72 | 3 | 0
2.1.1.2 | Version 1.0 | Wed 2/12/14 | Tue 2/18/14 | 70 | 0 | 0
2.1.2 | Test Plan | Wed 2/5/14 | Tue 2/18/14 | 100 | 0 | 0
2.2 | Prototype Implementation | Tue 2/18/14 | Thu 5/15/14 | 500 | 0 | 0
2.2.1 | Version 0.0 | Tue 2/18/14 | Tue 3/4/14 | 100 | 0 | 0
2.2.2 | Version 1.0 | Tue 3/4/14 | Tue 3/18/14 | 100 | 0 | 0
2.2.3 | Version 2.0 | Tue 3/18/14 | Tue 4/1/14 | 100 | 0 | 0
2.2.4 | Version 3.0 | Tue 4/1/14 | Tue 4/15/14 | 100 | 0 | 0
2.2.5 | Final Product | Tue 4/15/14 | Tue 4/29/14 | 100 | 0 | 0
2.3 | Final Documetation | Tue 4/1/14 | Tue 4/29/14 | 10 | 0 | 0
3 | Presentations | Fri 9/13/13 | Fri 4/25/14 | 42 | 28 | 80.95
3.5 | Team Stauts Report SD2 | Thu 1/23/14 | Fri 4/25/14 | 8 | 1 | 0
4 | Team Meetings | Tue 9/10/13 | Tue 12/9/14 | 480 | 130 | 53.33
4.2 | Team Meeting SD2 | Tue 1/14/14 | Thu 5/1/14 | 256 | 22 | 12.5
5 | Sponser Meetings | Tue 9/9/14 | Tue 9/9/14 | 30 | 8 | 0
6 | MS Project | Sun 9/29/13 | Thu 10/23/14 | 40 | 23 | 50
6.2 | SD 2 | Thu 1/23/14 | Thu 1/23/14 | 20 | 1 | 0

## Slide 3: ADS Changes
Redrew UI Layer to MVC
Updated Data Flow Numbering
Added Traceability Matrix
Rewrote Layer introduction
Tradeoffs
Testing Considerations
OS Requirements

## Slide 4: ADS Changes – U.I. Layer
Condensed Subsystems of the U.I. Layer
  BEFORE: Configuration, Import, Print, Status, Database
  AFTER: GUI, Controller, Database
Changed “Modules” to “Subsystems”
Updated Inter-Subsystem Data Flow Chart.

## Slide 5: Before

## Slide 6: After

## Slide 7: ADS Changes – Tradeoffs Testing
Tradeoffs
  Simple Interface Layer
  Three Processing Layers vs. One Processing Layer
  Physical and Printer Feedback Layer Separated
Testing Considerations
  Emphasized Testing Layers Independently

## Slide 8: ADS Changes – OS Requirements
Language requirements
VM needs
TXRX required
Windows XP S.P. 3