## Sheet1
Id | Rank | Category | Risk | Probability | Cost(Days) | Exposure | Possible Solution | Found By
1 | High | Software | Slic3r is unsuited for the task as-is | 50% | 45 | 22.5
2 | Medium | Team | Analytic Geometry skills not sufficient | 25% | 45 | 11.25
3 | Low | Team | Hardware selection is not specified correctly | 50% | 60 | 30
4 | Low | Team | Computer engineer over encumbered with tasks | 50% | 20 | 10