## Slide 1: Team Ink3D Status 3/28/14
Daniel Lain
Tim Edmonson
Shawn Simonson
Jesse Bowles

## Slide 2: Project Status
Task Number | Task Name | Planned Start | Planned Finish | Planned Work Hours | Actual Work Hours | % Work Completed | Earned Vaule
2 | Senior Design 2 | Wed 1/15/14 | Fri 5/23/14 | 762 | 307 | 33.07 | 252
2.1 | Documents | Wed 1/15/14 | Fri 5/23/14 | 242 | 256 | 100 | 242
2.1.1 | Detailed Design Documnetation | Tue 1/21/14 | Fri 2/28/14 | 142 | 212 | 100 | 142
2.1.1.1 | Version 1.0 | Tue 1/21/14 | Thu 2/20/14 | 72 | 208 | 100 | 72
2.1.1.2 | Version 2.0 | Wed 2/12/14 | Fri 2/28/14 | 70 | 4 | 100 | 70
2.1.2 | Test Plan | Thu 2/20/14 | Tue 3/18/14 | 100 | 44 | 100 | 100
2.2 | Prototype Implementation | Tue 2/18/14 | Thu 5/15/14 | 500 | 46 | 0 | 0
2.2.1 | Version 0.0 | Tue 3/18/14 | Tue 4/1/14 | 100 | 46 | 0 | 0
2.2.2 | Version 0.5 | Tue 3/4/14 | Tue 3/18/14 | 100 | 0 | 0 | 0
2.2.3 | Version 1.0 | Tue 3/18/14 | Tue 4/1/14 | 100 | 0 | 0 | 0
2.2.4 | Version 2.0 | Tue 4/1/14 | Tue 4/15/14 | 100 | 0 | 0 | 0
2.2.5 | Final Product | Tue 4/15/14 | Tue 4/29/14 | 100 | 0 | 0 | 0
2.3 | Final Documetation | Tue 4/1/14 | Tue 4/29/14 | 10 | 0 | 0 | 0
2.4 | Architecture Design Version 2.1 | Tue 1/21/14 | Mon 2/24/14 | 10 | 5 | 100 | 10
3 | Presentations | Fri 9/13/13 | Fri 4/25/14 | 49 | 49 | 89.8 | 44
3.4 | Detailed Design Review | Thu 2/20/14 | Tue 2/25/14 | 7 | 18 | 100 | 7
3.6 | Team Stauts Report SD2 | Thu 1/23/14 | Fri 4/25/14 | 8 | 4 | 37.5 | 3
4 | Team Meetings | Tue 9/10/13 | Tue 12/9/14 | 496 | 209 | 83.87 | 416
4.2 | Team Meeting SD2 | Tue 1/14/14 | Thu 5/1/14 | 272 | 101 | 70.59 | 192
5 | Sponser Meetings | Mon 9/9/13 | Tue 9/9/14 | 30 | 20 | 0 | 0
6 | MS Project | Sun 9/29/13 | Thu 10/23/14 | 40 | 30 | 50 | 20
6.2 | SD 2 | Thu 1/23/14 | Thu 1/23/14 | 20 | 8 | 0 | 0

## Slide 3: Database
Implemented
  24/24 Commands in CommandStructure
  XmlPersistenceFramework
  24/26 Tests (complete by Tuesday)
    XmlPersistenceFramework
    GetPrintJobConfguration
Issues
  Rethink DB and Mater Configuration
  JaxB Issue

## Slide 4: GUI Progress

## Slide 5: GUI Progress

## Slide 6: Processing Layers
Implementations Completed
  Object File Translation Module
  Subsection Module
Testing Completed
  Object File Translation Module
In progress
  Subsection Module Testing
  Slicing Engine Module Implementation
By Tuesday
  Processing Layers complete (implementation and testing)

## Slide 7: Communications Layer Updates
Progress
Test program tested on virtual serial device
Live test session scheduled for next week
Communications layer (first iteration) on track for completion 4/1
Issues
Printer access
Multiple Windows drivers for printer hardware. (May be trial and error)
Looking Forward
Finalize communications layer based on live tests
Begin implementation of Printer Control Layer

## Slide 8: Next Steps
Finish Stage One
  DB
  Processing Layers
  Communications Layer
Start Stage Two
  GUI / Controller part 1
  Printer Control Layer