## Slide 1: Team Ink3D Charter / Plan Review
Daniel Lain
Tim Edmonson
Shawn Simonson
Jesse Bowles

## Slide 2: Organization
Oversight – Dr. Shiakolas , Mr. O’Dell
Constraints
Assumptions
Role | Assigned To | Responsibility
Project Manager | Daniel Lain | Maintain Project Plan Assign Tasks to Team Turn in Deliverables Risk Manager Change Approval
Hardware Lead | Shawn Simonson | Plan Hardware Interfaces Research Hardware Hardware Development ME Liaison Change Approval
Software Engineering Lead | Jesse Bowles | System Architecture Modular Planning Scalability Planning Develop UMLs Change Approval
Lead Programmer | Tim Edmonson | Algorithm Development Open Source Selection Algorithm Research Change Approval

## Slide 3: Work Breakdown Structure
Task Number | Task Name | Planned Start | Actual Start | Planned Finish | Actual Finish | Planned Work Hours
1 | Senior Design 1 | Wed 9/11/13 | Wed 9/11/13 | Wed 12/11/13 | NA | 315
1.1 | Documents | Wed 9/11/13 | Wed 9/11/13 | Wed 12/11/13 | NA | 315
1.1.1 | System Requirements Specification | Wed 9/11/13 | Wed 9/11/13 | Fri 11/8/13 | NA | 118
1.1.1.1 | Version 0.0 | Wed 9/11/13 | Wed 9/11/13 | Wed 10/9/13 | NA | 57
1.1.1.2 | Version 1.0 | Wed 10/9/13 | Wed 10/9/13 | Fri 11/8/13 | NA | 31
1.1.1.3 | Version 2.0 | Wed 10/9/13 | NA | Thu 11/7/13 | NA | 30
1.1.2 | Team Charter | Thu 10/3/13 | Thu 10/3/13 | Wed 12/11/13 | NA | 102
1.1.2.1 | Version 0.0 | Thu 10/3/13 | Thu 10/3/13 | Thu 10/24/13 | Thu 10/24/13 | 44
1.1.2.2 | Version 1.0 | Thu 10/17/13 | NA | Thu 11/7/13 | NA | 28
1.1.2.3 | Version 2.0 | Mon 10/28/13 | NA | Wed 12/11/13 | NA | 30
1.1.3 | Architecture Design Specification | Fri 11/1/13 | NA | Wed 12/11/13 | NA | 95
1.1.3.1 | Version 0.0 | Fri 11/1/13 | NA | Mon 12/2/13 | NA | 35
1.1.3.2 | Version 1.0 | Tue 12/3/13 | NA | Wed 12/11/13 | NA | 30
1.1.3.3 | Version 2.0 | Tue 12/3/13 | NA | Wed 12/11/13 | NA | 30
2 | Senior Design 2 | Wed 1/15/14 | NA | Fri 5/23/14 | NA | 261
2.1 | Documents | Wed 1/15/14 | NA | Fri 5/23/14 | NA | 111
2.1.1 | Detailed Design Documnetation | Wed 1/15/14 | NA | Tue 2/18/14 | NA | 71
2.1.1.1 | Version 0.0 | Wed 1/15/14 | NA | Wed 2/12/14 | NA | 36
2.1.1.2 | Version 1.0 | Wed 2/12/14 | NA | Tue 2/18/14 | NA | 35
2.1.2 | Test Plan |  | NA |  | NA | 40
2.2 | Prototype Implementation | Tue 2/18/14 | NA | Thu 5/15/14 | NA | 150
2.2.1 | Version 0.0 | Tue 2/18/14 | NA | Tue 3/18/14 | NA | 50
2.2.2 | Version 1.0 | Tue 3/18/14 | NA | Fri 4/18/14 | NA | 50
2.2.3 | Final Product | Fri 4/18/14 | NA | Thu 5/15/14 | NA | 50
3 | Presentations | Fri 9/13/13 | NA | Wed 12/11/13 | NA | 28
3.1 | SRS Gate Review | Wed 10/9/13 | NA | Fri 11/8/13 | NA | 7
3.2 | Charter and Plan Review | Wed 10/16/13 | NA | Wed 12/4/13 | NA | 7
3.3 | Architecture Design Review | Mon 12/2/13 | NA | Wed 12/11/13 | NA | 7
3.4 | Team Status Report SD 1 | Fri 9/13/13 | NA | Fri 12/6/13 | NA | 7
4 | Team Meetings | Tue 9/10/13 | Tue 9/10/13 | Tue 12/3/13 | NA | 52
4.1 | Team Meeting SD1 | Tue 9/10/13 | Tue 9/10/13 | Tue 12/3/13 | NA | 52
5 | Sponser Meetings | Mon 9/9/13 | NA | Mon 9/9/13 | NA | 0
6 | MS Project | Sun 9/29/13 | Sun 9/29/13 | Fri 1/10/14 | NA | 40
6.1 | SD 1 | Sun 9/29/13 | Sun 9/29/13 | Wed 12/4/13 | NA | 20
6.2 | SD 2 | Fri 1/10/14 | NA | Fri 1/10/14 | NA | 20

## Slide 4: Quality Management
Documentation
  Engineering Notebooks
  Deliverables
  Status Reports
    Internal reports
    External reports
Software
  University Trained
  Top-Down approach
  GitHub
Hardware
  ME Team builds most hardware
  Ink3D constructing additional test

## Slide 5: Internal Communication
Team Meetings
  Every Tuesday and Thursday (sometimes Sunday)
  Agenda written before each meeting
GitHub
  Version Control
  Advantage: Supports multiple OS’s
E-mail
  Preferred over text-message
  Team has proven to be quick to respond.

## Slide 6: External Communication
  Dr. Shiakolas (Team Sponsor)
    E-mail
    Sponsor-Team Meeting
  Mr. O’Dell (Professor)
    E-mail
    Class
    Office Hours
  Mechanical Engineering Team
    E-mail
    Team Meeting

## Slide 7: Procurement
Begins One of Two Ways:
    Individual Team Member
    Team Concludes a Need from Discussion
  If Individual requests procurement
    Individual’s responsibility to research cost, use, and feasibility
    Present results at next meeting.
  If Team requests procurement
    One or more individual is assigned to research item,
    Present(s) results at next meeting

## Slide 8: Procurement Responsibilities
Project Sponsor: Dr. Shiakolas
    Already Providing lots of equipment
    Gives advice on what to procure
Project Team
    Choose what to procure
    Choose how to procure
Project Manager: Daniel Lain
    Oversees procurement process
Mr. O’Dell
    Approves/Denies procurement request
    Controls budget

## Slide 9: Scope Statement
Introduction to 3D Printer Fabrication System
Product Definition
  Host machine and operator
  Intermediate compact machine issues instructions to printer controller
  Printer controller
Audience
  Dr. Shiakolas
  Mechanical Engineering team
  CNC machinists and experienced fabricators

## Slide 10: Cost Management
Cost management plan provides procedure for dealing with project costs.
Cost and Labor Management
  Cost and labor managed by the project manager.
  Labor breakdown kept in Microsoft Project Plan
Performance Cost
  Maintained by project manager
  Metrics: BCWS, BCWP, ACWP
Material Cost
  Joint venture between CpE team and ME team
  Must be agreed upon between CpE team, Dr. Shiakolas and his team, and Mr. O’Dell.

## Slide 11: Risk Management
Identify Roles
  Project Sponsor: Dr. Shiakolas (Mechanical Engineering)
  Project Manager: Dan Lain
  Project Stakeholders: Dr. Shiakolas, ME team, machine operators, CpE team
  Risk Manager: Dan Lain
  Project Team responsibilities: Identify risk, scope of risk, and document the risk so that it can be presented to the project manager and the rest of the team
Risk Triggers
  Slic3r, excessive research time, hardware failures, only one person with extensive hardware experience between both teams.
Risk Analysis and Severity
  Risks probability identified and categorized in order of severity in terms of impact on the team
Risk Response
  Risk Manager works with team to develop plan of action when risks have been identified and presented
  Risk Response is a continual process. Conducted during team meetings.
Risk Documentation
  Spreadsheet will provide a quick-look table of risks identified by team members.
  Hosted on Git repository
  All-access.

## Slide 12: Earned Value Management
Reported to Project Manager each week through Individual Status Reports
  ACWP (Actual Cost)
  Actual Start
  Actual Finish
Maintained in Project Plan
  BCWS (Planned Value)
  BCWP (Earned Value)
Reviewed to refine Project Plan
  CPI
  SPI

## Slide 13: Scope Management Plan
Scope defined through SRS and WBS
Controlled through Team Member Accountability
Deliverables verified based on SRS and WBS
  Concerns will be discussed with team members and the project sponsor
Scope changes may be proposed by team members or the project sponsor

## Slide 14: Change Management
Many unknowns involved in our project
Process
  Potential Change Identified
  Change Control Form presented to Project Manager
  Project Manager presents the changes to the team
  Team discusses changes
  Team Approval
  Sponsor Approval
All proposed changes will be documented using the Change Control Form

## Slide 15: Closeout Report
Capture Analysis of:
  Project Objectives
  Lessons Learned
Post Implementation Review
  Does the project meet specifications?
  Was the scope realistic for the project?
Customer Acceptance
  Verify based on SRS
  Discuss open issues
Project Performance Report
  Performance based on Earned Value Management
  Quality, Risk, Scope Management Performance
Archive Records
  Project Artifacts
  Financial Records