## Raw
Task Number | Task Name | Predecessors | Resource Initials | Planned Start | Actual Start | Planned Finish | Actual Finish | Planned Work Hours | Actual Work Hours | % Work Completed | Earned Vaule
1.1.1.1.1 | Meet with Sponser |  | Dan,Jesse,Tim | Wed 9/11/13 | Wed 9/11/13 | Wed 9/11/13 | Wed 9/11/13 | 3 | 3 | 100 | 3
1.1.1.1.2 | Derive Requirements |  | Team | Tue 9/17/13 | Tue 9/17/13 | Thu 9/19/13 | Thu 9/19/13 | 3 | 3 | 100 | 3
1.1.1.1.3 | Product Concept |  | Dan | Tue 9/17/13 | Tue 9/17/13 | Thu 9/19/13 | Thu 9/19/13 | 1 | 1 | 100 | 1
1.1.1.1.4 | Product Description & Functional Overview |  | Jesse | Thu 9/19/13 | Thu 9/19/13 | Tue 9/24/13 | Tue 9/24/13 | 2 | 2 | 100 | 2
1.1.1.1.5 | Customer Requirements | 6 | Jesse,Shawn,Tim | Tue 9/24/13 | Tue 9/24/13 | Thu 10/3/13 | Thu 10/3/13 | 4 | 5.5 | 100 | 4
1.1.1.1.6 | Packaging Requirements | 6 | Tim | Tue 9/24/13 | Tue 9/24/13 | Thu 10/3/13 | Thu 10/3/13 | 4 | 1 | 100 | 4
1.1.1.1.7 | Performance Requirements | 6 | Tim | Tue 9/24/13 | Tue 9/24/13 | Thu 10/3/13 | Thu 10/3/13 | 4 | 1 | 100 | 4
1.1.1.1.8 | Saftey Requirements | 6 | Tim | Tue 9/24/13 | Tue 9/24/13 | Thu 10/3/13 | Thu 10/3/13 | 4 | 1 | 100 | 4
1.1.1.1.9 | Maintenance & Support Requirements | 6 | Shawn | Tue 9/24/13 | Tue 9/24/13 | Thu 10/3/13 | Thu 10/3/13 | 4 | 1 | 100 | 4
1.1.1.1.10 | Other Requirements | 6 | Tim | Tue 9/24/13 | Tue 9/24/13 | Thu 10/3/13 | Thu 10/3/13 | 4 | 1 | 100 | 4
1.1.1.1.11 | Acceptance Criteria | 9,10,11,12,13,14 | Dan | Tue 9/24/13 | Tue 9/24/13 | Thu 10/3/13 | Thu 10/3/13 | 2 | 1 | 100 | 2
1.1.1.1.12 | Use Cases | 6 | Jesse | Tue 9/24/13 | Tue 9/24/13 | Thu 10/3/13 | Thu 10/3/13 | 2 | 1 | 100 | 2
1.1.1.1.13 | Feasibility Assessment | 6 | Tim,Shawn,Jesse | Tue 9/24/13 | Tue 9/24/13 | Thu 10/3/13 | Thu 10/3/13 | 2 | 3 | 100 | 2
1.1.1.1.14 | Future Items |  | Tim | Tue 9/24/13 | Tue 9/24/13 | Thu 10/3/13 | Thu 10/3/13 | 2 | 1 | 100 | 2
1.1.1.1.15 | Rough Draft Compliation |  | Dan | Thu 10/3/13 | Thu 10/3/13 | Thu 10/3/13 | Thu 10/3/13 | 12 | 17 | 100 | 12
1.1.1.1.16.1 | Product Concept |  | Jesse | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | 1 | 1 | 100 | 1
1.1.1.1.16.2 | Product Description & Functional Overview |  | Tim | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | 1 | 1 | 100 | 1
1.1.1.1.16.3 | Customer Requirements |  | Dan | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | 1 | 1 | 100 | 1
1.1.1.1.16.4 | Packaging Requirements |  | Dan | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | 1 | 1 | 100 | 1
1.1.1.1.16.5 | Performance Requirements |  | Dan | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | 1 | 1 | 100 | 1
1.1.1.1.16.6 | Saftey Requirements |  | Dan | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | 1 | 1 | 100 | 1
1.1.1.1.16.7 | Maintenance & Support Requirements |  | Dan | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | 1 | 1 | 100 | 1
1.1.1.1.16.8 | Other Requirements |  | Dan | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | 1 | 1 | 100 | 1
1.1.1.1.16.9 | Acceptance Criteria |  | Shawn | Sat 10/5/13 | Sat 10/5/13 | Sun 10/6/13 | Sun 10/6/13 | 1 | 1 | 100 | 1
1.1.1.1.16.10 | Use Cases |  | Tim | Sat 10/5/13 | Sat 10/5/13 | Sun 10/6/13 | Sun 10/6/13 | 1 | 2 | 100 | 1
1.1.1.1.16.11 | Feasibility Assessment |  | Jesse,Shawn | Sat 10/5/13 | Sat 10/5/13 | Sun 10/6/13 | Sun 10/6/13 | 1 | 5 | 100 | 1
1.1.1.1.16.12 | Future Items |  | Shawn | Sat 10/5/13 | Sat 10/5/13 | Tue 10/8/13 | Tue 10/8/13 | 1 | 1 | 100 | 1
1.1.1.1.17 | Team Revisions |  |  | Sat 10/5/13 | Sat 10/5/13 | Wed 10/9/13 | Wed 10/9/13 | 1 | 1 | 100 | 1
1.1.1.1.18 | Deliver SRS |  |  | Wed 10/9/13 | Wed 10/9/13 | Wed 10/9/13 | Wed 10/9/13 | 1 | 0 | 100 | 1
1.1.1.1.19.1 | Derive Requirements |  | Team | Sat 10/5/13 | Sat 10/5/13 | Mon 11/4/13 | Mon 11/4/13 | 1 | 0 | 100 | 1
1.1.1.1.19.2 | Product Concept |  | Dan | Sat 10/5/13 | Sat 10/5/13 | Mon 11/4/13 | Mon 11/4/13 | 1 | 0 | 100 | 1
1.1.1.1.19.3 | Product Description & Functional Overview |  | Jesse | Sat 10/5/13 | Sat 10/5/13 | Mon 11/4/13 | Mon 11/4/13 | 1 | 1 | 100 | 1
1.1.1.1.19.4 | Customer Requirements |  | Jesse,Shawn,Tim | Sat 10/5/13 | Sat 10/5/13 | Mon 11/4/13 | Mon 11/4/13 | 1 | 0 | 100 | 1
1.1.1.1.19.5 | Packaging Requirements |  | Tim | Sat 10/5/13 | Sat 10/5/13 | Mon 11/4/13 | Mon 11/4/13 | 1 | 0 | 100 | 1
1.1.1.1.19.6 | Performance Requirements |  | Tim | Sat 10/5/13 | Sat 10/5/13 | Mon 11/4/13 | Mon 11/4/13 | 1 | 0 | 100 | 1
1.1.1.1.19.7 | Saftey Requirements |  | Tim | Sat 10/5/13 | Sat 10/5/13 | Mon 11/4/13 | Mon 11/4/13 | 1 | 0 | 100 | 1
1.1.1.1.19.8 | Maintenance & Support Requirements |  | Shawn | Sat 10/5/13 | Sat 10/5/13 | Mon 11/4/13 | Mon 11/4/13 | 1 | 1 | 100 | 1
1.1.1.1.19.9 | Other Requirements |  | Tim | Sat 10/5/13 | Sat 10/5/13 | Mon 11/4/13 | Mon 11/4/13 | 1 | 0 | 100 | 1
1.1.1.1.19.10 | Acceptance Criteria |  | Dan | Mon 10/7/13 | Mon 10/7/13 | Mon 11/4/13 | Mon 11/4/13 | 1 | 0 | 100 | 1
1.1.1.1.19.11 | Use Cases |  | Jesse | Sat 10/5/13 | Sat 10/5/13 | Mon 11/4/13 | Mon 11/4/13 | 1 | 0 | 100 | 1
1.1.1.1.19.12 | Feasibility Assessment |  | Tim,Shawn,Jesse | Sat 10/5/13 | Sat 10/5/13 | Mon 11/4/13 | Mon 11/4/13 | 4 | 8 | 100 | 4
1.1.1.1.19.13 | Future Items |  | Tim | Sat 10/5/13 | Sat 10/5/13 | Mon 11/4/13 | Mon 11/4/13 | 1 | 0 | 100 | 1
1.1.1.1.20 | SRS Gate Review |  |  | Mon 11/4/13 | Mon 11/4/13 | Mon 11/4/13 | Mon 11/4/13 | 1 | 1 | 100 | 1
1.1.1.2.1 | Meet with Sponser |  | Team | Wed 10/30/13 | Wed 10/30/13 | Wed 10/30/13 | Wed 10/30/13 | 3 | 3 | 100 | 3
1.1.1.2.2 | Product Concept |  |  | Wed 10/30/13 | Wed 10/30/13 | Mon 11/4/13 | Mon 11/4/13 | 1 | 0 | 100 | 1
1.1.1.2.3 | Product Description & Functional Overview |  |  | Wed 10/30/13 | Wed 10/30/13 | Mon 11/4/13 | Mon 11/4/13 | 4 | 0 | 100 | 4
1.1.1.2.4 | Customer Requirements |  |  | Wed 10/30/13 | Wed 10/30/13 | Mon 11/4/13 | Mon 11/4/13 | 2 | 0 | 100 | 2
1.1.1.2.5 | Packaging Requirements |  |  | Wed 10/30/13 | Wed 10/30/13 | Mon 11/4/13 | Mon 11/4/13 | 2 | 0 | 100 | 2
1.1.1.2.6 | Performance Requirements |  |  | Wed 10/30/13 | Wed 10/30/13 | Mon 11/4/13 | Mon 11/4/13 | 2 | 0 | 100 | 2
1.1.1.2.7 | Saftey Requirements |  |  | Wed 10/30/13 | Wed 10/30/13 | Mon 11/4/13 | Mon 11/4/13 | 2 | 0 | 100 | 2
1.1.1.2.8 | Maintenance & Support Requirements |  |  | Wed 10/30/13 | Wed 10/30/13 | Mon 11/4/13 | Mon 11/4/13 | 2 | 0 | 100 | 2
1.1.1.2.9 | Other Requirements |  |  | Wed 10/30/13 | Wed 10/30/13 | Mon 11/4/13 | Mon 11/4/13 | 2 | 0 | 100 | 2
1.1.1.2.10 | Acceptance Criteria |  |  | Wed 10/30/13 | Wed 10/30/13 | Mon 11/4/13 | Mon 11/4/13 | 2 | 0 | 100 | 2
1.1.1.2.11 | Use Cases |  |  | Wed 10/30/13 | Wed 10/30/13 | Mon 11/4/13 | Mon 11/4/13 | 2 | 0 | 100 | 2
1.1.1.2.12 | Feasibility Assessment |  |  | Wed 10/30/13 | Wed 10/30/13 | Mon 11/4/13 | Mon 11/4/13 | 2 | 0 | 100 | 2
1.1.1.2.13 | Future Items |  |  | Wed 10/30/13 | Wed 10/30/13 | Mon 11/4/13 | Mon 11/4/13 | 2 | 0 | 100 | 2
1.1.1.2.14 | Final Draft |  |  | Wed 10/30/13 | Wed 10/30/13 | Mon 11/4/13 | Mon 11/4/13 | 2 | 5 | 100 | 2
1.1.1.3.1 | Meet with Sponser |  | Dan,Jesse,Tim | Wed 10/30/13 | Wed 10/30/13 | Wed 11/20/13 | Wed 11/20/13 | 3 | 6 | 100 | 3
1.1.1.3.2 | Product Concept |  | Team | Wed 10/30/13 | Wed 10/30/13 | Mon 11/18/13 | Mon 11/18/13 | 1 | 1 | 100 | 1
1.1.1.3.3 | Product Description & Functional Overview |  | Team | Wed 10/30/13 | Wed 10/30/13 | Mon 11/18/13 | Mon 11/18/13 | 4 | 1 | 100 | 4
1.1.1.3.4 | Customer Requirements |  | Team | Wed 10/30/13 | Wed 10/30/13 | Mon 11/18/13 | Mon 11/18/13 | 2 | 1 | 100 | 2
1.1.1.3.5 | Packaging Requirements |  | Team | Wed 10/30/13 | Wed 10/30/13 | Mon 11/18/13 | Mon 11/18/13 | 2 | 1 | 100 | 2
1.1.1.3.6 | Performance Requirements |  | Team | Wed 10/30/13 | Wed 10/30/13 | Mon 11/18/13 | Mon 11/18/13 | 2 | 1 | 100 | 2
1.1.1.3.7 | Saftey Requirements |  | Team | Wed 10/30/13 | Wed 10/30/13 | Mon 11/18/13 | Mon 11/18/13 | 2 | 1 | 100 | 2
1.1.1.3.8 | Maintenance & Support Requirements |  | Team | Wed 10/30/13 | Wed 10/30/13 | Mon 11/18/13 | Mon 11/18/13 | 2 | 1 | 100 | 2
1.1.1.3.9 | Other Requirements |  | Team | Wed 10/30/13 | Wed 10/30/13 | Mon 11/18/13 | Mon 11/18/13 | 2 | 1 | 100 | 2
1.1.1.3.10 | Acceptance Criteria |  | Team | Wed 10/30/13 | Wed 10/30/13 | Mon 11/18/13 | Mon 11/18/13 | 2 | 1 | 100 | 2
1.1.1.3.11 | Use Cases |  | Team | Wed 10/30/13 | Wed 10/30/13 | Mon 11/18/13 | Mon 11/18/13 | 2 | 1 | 100 | 2
1.1.1.3.12 | Feasibility Assessment |  | Team | Wed 10/30/13 | Wed 10/30/13 | Mon 11/18/13 | Mon 11/18/13 | 2 | 1 | 100 | 2
1.1.1.3.13 | Future Items |  | Team | Wed 10/30/13 | Wed 10/30/13 | Mon 11/18/13 | Mon 11/18/13 | 2 | 1 | 100 | 2
1.1.1.3.14 | Final Draft |  | Team | Wed 10/30/13 | Wed 10/30/13 | Mon 11/18/13 | Mon 11/18/13 | 2 | 1 | 100 | 2
1.1.2.1.1 | General Organization |  | Dan | Thu 10/3/13 | Thu 10/3/13 | Thu 10/10/13 | Thu 10/10/13 | 2 | 2 | 100 | 2
1.1.2.1.2 | Scope Statement |  | Shawn | Thu 10/3/13 | Thu 10/3/13 | Thu 10/10/13 | Thu 10/10/13 | 2 | 2 | 100 | 2
1.1.2.1.3 | Cost Management Plan |  | Shawn | Thu 10/3/13 | Thu 10/3/13 | Thu 10/10/13 | Thu 10/10/13 | 2 | 2 | 100 | 2
1.1.2.1.4 | Earned Value Management |  | Tim | Thu 10/3/13 | Thu 10/3/13 | Thu 10/10/13 | Thu 10/10/13 | 2 | 1 | 100 | 2
1.1.2.1.5 | Scope Management Plan |  | Tim | Thu 10/3/13 | Thu 10/3/13 | Thu 10/10/13 | Thu 10/10/13 | 2 | 2 | 100 | 2
1.1.2.1.6 | Work Breakdown Srtucture |  | Dan | Thu 10/3/13 | Thu 10/3/13 | Thu 10/10/13 | Thu 10/10/13 | 6 | 6 | 100 | 6
1.1.2.1.7 | Quality Management Plan |  | Jesse | Thu 10/3/13 | Thu 10/3/13 | Thu 10/10/13 | Thu 10/10/13 | 2 | 1 | 100 | 2
1.1.2.1.8 | Communication Plan |  | Jesse | Thu 10/3/13 | Thu 10/3/13 | Thu 10/10/13 | Thu 10/10/13 | 2 | 1 | 100 | 2
1.1.2.1.9 | Change Management Plan |  | Tim | Thu 10/3/13 | Thu 10/3/13 | Thu 10/10/13 | Thu 10/10/13 | 2 | 2 | 100 | 2
1.1.2.1.10 | Risk Management Plan |  | Shawn | Thu 10/3/13 | Thu 10/3/13 | Thu 10/10/13 | Thu 10/10/13 | 2 | 3 | 100 | 2
1.1.2.1.11 | Procurement Management Plan |  | Jesse | Thu 10/3/13 | Thu 10/3/13 | Thu 10/10/13 | Thu 10/10/13 | 2 | 2 | 100 | 2
1.1.2.1.12 | Project Closeout Report |  | Tim | Thu 10/3/13 | Thu 10/3/13 | Thu 10/10/13 | Thu 10/10/13 | 2 | 1 | 100 | 2
1.1.2.1.13.1 | General Organization |  | Tim | Thu 10/10/13 | Thu 10/10/13 | Sun 10/13/13 | Sun 10/13/13 | 1 | 1 | 100 | 1
1.1.2.1.13.2 | Scope Statement |  | Jesse | Thu 10/10/13 | Thu 10/10/13 | Sun 10/13/13 | Sun 10/13/13 | 1 | 1 | 100 | 1
1.1.2.1.13.3 | Cost Management Plan |  | Dan | Thu 10/10/13 | Thu 10/10/13 | Sun 10/13/13 | Sun 10/13/13 | 1 | 1 | 100 | 1
1.1.2.1.13.4 | Earned Value Management |  | Shawn | Thu 10/10/13 | Thu 10/10/13 | Sun 10/13/13 | Sun 10/13/13 | 1 | 1 | 100 | 1
1.1.2.1.13.5 | Scope Management Plan |  | Jesse | Thu 10/10/13 | Thu 10/10/13 | Sun 10/13/13 | Sun 10/13/13 | 1 | 1 | 100 | 1
1.1.2.1.13.6 | Work Breakdown Srtucture |  | Tim | Thu 10/10/13 | Thu 10/10/13 | Sun 10/13/13 | Sun 10/13/13 | 1 | 1 | 100 | 1
1.1.2.1.13.7 | Quality Management Plan |  | Dan | Thu 10/10/13 | Thu 10/10/13 | Sun 10/13/13 | Sun 10/13/13 | 1 | 0 | 100 | 1
1.1.2.1.13.8 | Communication Plan |  | Shawn | Thu 10/10/13 | Thu 10/10/13 | Sun 10/13/13 | Sun 10/13/13 | 1 | 1 | 100 | 1
1.1.2.1.13.9 | Change Management Plan |  | Jesse | Thu 10/10/13 | Thu 10/10/13 | Sun 10/13/13 | Sun 10/13/13 | 1 | 0 | 100 | 1
1.1.2.1.13.10 | Risk Management Plan |  | Tim | Thu 10/10/13 | Thu 10/10/13 | Sun 10/13/13 | Sun 10/13/13 | 1 | 1 | 100 | 1
1.1.2.1.13.11 | Procurement Management Plan |  | Shawn | Thu 10/10/13 | Thu 10/10/13 | Sun 10/13/13 | Sun 10/13/13 | 1 | 0 | 100 | 1
1.1.2.1.13.12 | Project Closeout Report |  | Dan | Thu 10/10/13 | Thu 10/10/13 | Sun 10/13/13 | Sun 10/13/13 | 1 | 0 | 100 | 1
1.1.2.1.14 | Team Changes |  |  | Sun 10/13/13 | Sun 10/13/13 | Sun 10/13/13 | Sun 10/13/13 | 2 | 0 | 100 | 2
1.1.2.1.15 | First Draft Charter |  |  | Thu 10/24/13 | Thu 10/24/13 | Thu 10/24/13 | Thu 10/24/13 | 2 | 0 | 100 | 2
1.1.2.2.1 | General Organization |  | Team | Thu 10/17/13 | Thu 10/17/13 | Tue 12/3/13 | Tue 12/3/13 | 2 | 1 | 100 | 2
1.1.2.2.2 | Scope Statement |  | Team | Thu 10/17/13 | Thu 10/17/13 | Tue 12/3/13 | Tue 12/3/13 | 2 | 1 | 100 | 2
1.1.2.2.3 | Cost Management Plan |  | Team | Thu 10/17/13 | Thu 10/17/13 | Tue 12/3/13 | Tue 12/3/13 | 2 | 1 | 100 | 2
1.1.2.2.4 | Earned Value Management |  | Team | Thu 10/17/13 | Thu 10/17/13 | Tue 12/3/13 | Tue 12/3/13 | 2 | 1 | 100 | 2
1.1.2.2.5 | Scope Management Plan |  | Team | Thu 10/17/13 | Thu 10/17/13 | Tue 12/3/13 | Tue 12/3/13 | 2 | 1 | 100 | 2
1.1.2.2.6 | Work Breakdown Srtucture |  | Team | Thu 10/17/13 | Thu 10/17/13 | Tue 12/3/13 | Tue 12/3/13 | 2 | 1 | 100 | 2
1.1.2.2.7 | Quality Management Plan |  | Team | Thu 10/17/13 | Thu 10/17/13 | Tue 12/3/13 | Tue 12/3/13 | 2 | 1 | 100 | 2
1.1.2.2.8 | Communication Plan |  | Team | Thu 10/17/13 | Thu 10/17/13 | Tue 12/3/13 | Tue 12/3/13 | 2 | 1 | 100 | 2
1.1.2.2.9 | Change Management Plan |  | Team | Thu 10/17/13 | Thu 10/17/13 | Tue 12/3/13 | Tue 12/3/13 | 2 | 1 | 100 | 2
1.1.2.2.10 | Risk Management Plan |  | Team | Thu 10/17/13 | Thu 10/17/13 | Tue 12/3/13 | Tue 12/3/13 | 2 | 1 | 100 | 2
1.1.2.2.11 | Procurement Management Plan |  | Team | Thu 10/17/13 | Thu 10/17/13 | Tue 12/3/13 | Tue 12/3/13 | 2 | 1 | 100 | 2
1.1.2.2.12 | Project Closeout Report |  | Team | Thu 10/17/13 | Thu 10/17/13 | Tue 12/3/13 | Tue 12/3/13 | 2 | 1 | 100 | 2
1.1.2.2.13 | Final Team Review |  | Team | Tue 11/5/13 | Tue 11/5/13 | Tue 12/3/13 | Tue 12/3/13 | 2 | 1 | 100 | 2
1.1.2.2.14 | Team Changes |  | Team | Tue 11/5/13 | Tue 11/5/13 | Tue 12/3/13 | Tue 12/3/13 | 2 | 1 | 100 | 2
1.1.3.1.1 | Brainstorm |  | Team | Tue 11/5/13 | Tue 11/5/13 | Tue 11/5/13 | Tue 11/5/13 | 2 | 5 | 100 | 2
1.1.3.1.2 | Introduction |  | Shawn | Fri 11/1/13 | Fri 11/1/13 | Fri 11/29/13 | Fri 11/29/13 | 2 | 1 | 100 | 2
1.1.3.1.3 | Meta Architecture |  | Tim | Fri 11/1/13 | Fri 11/1/13 | Fri 11/29/13 | Fri 11/29/13 | 3 | 2 | 100 | 3
1.1.3.1.4 | Layer Definitions |  | Dan | Fri 11/1/13 | Fri 11/1/13 | Fri 11/29/13 | Fri 11/29/13 | 3 | 2 | 100 | 3
1.1.3.1.5 | Inter-Subsystem Data Flow |  | Dan | Fri 11/1/13 | Fri 11/1/13 | Fri 11/29/13 | Fri 11/29/13 | 6 | 3 | 100 | 6
1.1.3.1.6 | Subsystem Descriptions |  | Jesse,Tim | Fri 11/1/13 | Fri 11/1/13 | Fri 11/29/13 | Fri 11/29/13 | 6 | 6 | 100 | 6
1.1.3.1.7 | Operatiing System Dependencies |  | Shawn | Fri 11/1/13 | Fri 11/1/13 | Fri 11/29/13 | Fri 11/29/13 | 3 | 2 | 100 | 3
1.1.3.1.8 | Testing Considerations |  | Shawn | Fri 11/1/13 | Fri 11/1/13 | Fri 11/29/13 | Fri 11/29/13 | 3 | 2 | 100 | 3
1.1.3.1.9 | Final Team Review |  | Team | Tue 12/3/13 | Tue 12/3/13 | Tue 12/3/13 | Tue 12/3/13 | 3 | 2 | 100 | 3
1.1.3.1.10 | Team Changes |  | Team | Tue 12/3/13 | Tue 12/3/13 | Tue 12/3/13 | Tue 12/3/13 | 3 | 1 | 100 | 3
1.1.3.1.11 | First Draft ADS |  | Team | Tue 12/3/13 | Tue 12/3/13 | Tue 12/3/13 | Tue 12/3/13 | 3 | 1 | 100 | 3
1.1.3.2.1 | Introduction |  | Shawn | Mon 12/9/13 | Mon 12/9/13 | Mon 12/9/13 | Mon 12/9/13 | 3 | 1 | 100 | 3
1.1.3.2.2 | Meta Architecture |  | Tim | Fri 11/29/13 | Fri 11/29/13 | Fri 11/29/13 | Fri 11/29/13 | 3 | 1 | 100 | 3
1.1.3.2.3 | Layer Definitions |  | Dan | Fri 11/29/13 | Fri 11/29/13 | Fri 11/29/13 | Fri 11/29/13 | 3 | 1 | 100 | 3
1.1.3.2.4 | Inter-Subsystem Data Flow |  | Dan | Fri 11/29/13 | Fri 11/29/13 | Fri 11/29/13 | Fri 11/29/13 | 3 | 1 | 100 | 3
1.1.3.2.5 | Subsystem Descriptions |  | Jesse,Tim | Fri 11/29/13 | Fri 11/29/13 | Fri 11/29/13 | Fri 11/29/13 | 3 | 1 | 100 | 3
1.1.3.2.6 | Operatiing System Dependencies |  | Jesse | Fri 11/29/13 | Fri 11/29/13 | Fri 11/29/13 | Fri 11/29/13 | 3 | 1 | 100 | 3
1.1.3.2.7 | Testing Considerations |  | Jesse | Fri 11/29/13 | Fri 11/29/13 | Fri 11/29/13 | Fri 11/29/13 | 3 | 1 | 100 | 3
1.1.3.2.8.1 | Introduction |  | Jesse | Fri 11/1/13 | Fri 11/1/13 | Fri 11/29/13 | Fri 11/29/13 | 2 | 1 | 100 | 2
1.1.3.2.8.2 | Meta Architecture |  | Dan | Fri 11/1/13 | Fri 11/1/13 | Fri 11/29/13 | Fri 11/29/13 | 2 | 1 | 100 | 2
1.1.3.2.8.3 | Layer Definitions |  | Shawn | Fri 11/1/13 | Fri 11/1/13 | Fri 11/29/13 | Fri 11/29/13 | 2 | 1 | 100 | 2
1.1.3.2.8.4 | Inter-Subsystem Data Flow |  | Shawn | Fri 11/1/13 | Fri 11/1/13 | Fri 11/29/13 | Fri 11/29/13 | 2 | 1 | 100 | 2
1.1.3.2.8.5 | Subsystem Descriptions |  | Dan,Tim | Fri 11/1/13 | Fri 11/1/13 | Fri 11/1/13 | Fri 11/1/13 | 2 | 1 | 100 | 2
1.1.3.2.8.6 | Operatiing System Dependencies |  | Jesse | Fri 11/1/13 | Fri 11/1/13 | Fri 11/29/13 | Fri 11/29/13 | 2 | 1 | 100 | 2
1.1.3.2.8.7 | Testing Considerations |  | Jesse | Fri 11/1/13 | Fri 11/1/13 | Fri 11/29/13 | Fri 11/29/13 | 2 | 1 | 100 | 2
1.1.3.2.9 | Final Team Review |  | Team | Fri 11/29/13 | Fri 11/29/13 | Fri 11/29/13 | Fri 11/29/13 | 3 | 1 | 100 | 3
1.1.3.2.10 | Team Changes |  | Team | Fri 11/29/13 | Fri 11/29/13 | Fri 11/29/13 | Fri 11/29/13 | 3 | 1 | 100 | 3
1.1.3.2.11 | ADS Gate Review |  | Team | Fri 11/29/13 | Fri 11/29/13 | Fri 11/29/13 | Fri 11/29/13 | 3 | 1 | 100 | 3
1.1.3.3.1 | Introduction |  | Shawn | Tue 12/3/13 | Tue 12/3/13 | Sat 1/18/14 | Sat 1/18/14 | 3 | 0 | 100 | 3
1.1.3.3.2 | Meta Architecture |  | Team | Fri 1/18/13 | Fri 1/18/13 | Sat 1/18/14 | Sat 1/18/14 | 3 | 1 | 100 | 3
1.1.3.3.3 | Layer Definitions |  | Dan | Fri 1/18/13 | Fri 1/18/13 | Sat 1/18/14 | Sat 1/18/14 | 3 | 1 | 100 | 3
1.1.3.3.4 | Inter-Subsystem Data Flow |  | Dan | Fri 1/18/13 | Fri 1/18/13 | Sat 1/18/14 | Sat 1/18/14 | 3 | 1 | 100 | 3
1.1.3.3.5 | Subsystem Descriptions |  | Jesse,Tim | Fri 1/18/13 | Fri 1/18/13 | Sat 1/18/14 | Sat 1/18/14 | 3 | 1.5 | 100 | 3
1.1.3.3.6 | Operatiing System Dependencies |  | Jesse | Mon 1/20/14 | Mon 1/20/14 | Mon 1/20/14 | Mon 1/20/14 | 3 | 4 | 100 | 3
1.1.3.3.7 | Testing Considerations |  | Jesse | Wed 1/15/14 | Wed 1/15/14 | Wed 1/15/14 | Wed 1/15/14 | 3 | 2 | 100 | 3
1.1.3.3.8 | Final Team Review |  | Team | Thu 12/5/13 | Thu 12/5/13 | Wed 1/15/14 | Wed 1/15/14 | 3 | 3 | 100 | 3
1.1.3.3.9 | Team Changes |  | Team | Tue 12/10/13 | Tue 12/10/13 | Wed 1/15/14 | Wed 1/15/14 | 3 | 2 | 100 | 3
1.1.3.3.10 | ADS Gate Review |  | Team | Wed 12/11/13 | Wed 12/11/13 | Wed 1/15/14 | Wed 1/15/14 | 3 | 1 | 100 | 3
2.1.1.1.1 | Introduction |  | Dan | Tue 1/21/14 | Tue 1/21/14 | Tue 2/18/14 | Tue 2/18/14 | 4 | 2 | 100 | 4
2.1.1.1.2 | Architecture Overview |  | Dan | Tue 1/21/14 | Tue 1/21/14 | Tue 2/18/14 | Tue 2/18/14 | 4 | 11 | 100 | 4
2.1.1.1.3 | Component Design |  | Team | Tue 1/21/14 | Tue 1/21/14 | Tue 2/18/14 | Tue 2/18/14 | 4 | 42 | 100 | 4
2.1.1.1.4 | Quality Assurance |  | Team | Tue 1/21/14 | Tue 1/21/14 | Tue 2/18/14 | Tue 2/18/14 | 4 | 1 | 100 | 4
2.1.1.1.5 | Test Plans and Procedures |  | Team | Tue 1/21/14 | Tue 1/21/14 | Tue 2/18/14 | Tue 2/18/14 | 4 | 6 | 100 | 4
2.1.1.1.6 | Test Cases |  | Team | Tue 1/21/14 | Tue 1/21/14 | Tue 2/18/14 | Tue 2/18/14 | 4 | 2 | 100 | 4
2.1.1.1.7 | Requirements Tracibility Matrix |  | Dan | Tue 1/21/14 | Tue 1/21/14 | Tue 2/18/14 | Tue 2/18/14 | 4 | 1 | 100 | 4
2.1.1.1.8 | Acceptance Plan |  | Dan | Tue 1/21/14 | Tue 1/21/14 | Tue 2/18/14 | Tue 2/18/14 | 4 | 1 | 100 | 4
2.1.1.1.9 | Packaging and Instalation |  | Dan | Tue 1/21/14 | Tue 1/21/14 | Tue 2/18/14 | Tue 2/18/14 | 4 | 1 | 100 | 4
2.1.1.1.10 | Acceptance Testing |  | Dan | Tue 1/21/14 | Tue 1/21/14 | Tue 2/18/14 | Tue 2/18/14 | 4 | 1 | 100 | 4
2.1.1.1.11 | Appendices |  | Tim | Tue 1/21/14 | Tue 1/21/14 | Tue 2/18/14 | Tue 2/18/14 | 4 | 1 | 100 | 4
2.1.1.1.12.1 | Introduction |  | Team | Tue 2/18/14 | Tue 2/18/14 | Tue 2/18/14 | Tue 2/18/14 | 2 | 2 | 100 | 2
2.1.1.1.12.2 | Architecture Overview |  | Team | Tue 2/18/14 | Tue 2/18/14 | Tue 2/18/14 | Tue 2/18/14 | 2 | 2 | 100 | 2
2.1.1.1.12.3 | Component Design |  | Team | Tue 2/18/14 | Tue 2/18/14 | Tue 2/18/14 | Tue 2/18/14 | 2 | 4 | 100 | 2
2.1.1.1.12.4 | Quality Assurance |  | Team | Tue 2/18/14 | Tue 2/18/14 | Tue 2/18/14 | Tue 2/18/14 | 2 | 2 | 100 | 2
2.1.1.1.12.5 | Test Plans and Procedures |  | Team | Tue 2/18/14 | Tue 2/18/14 | Tue 2/18/14 | Tue 2/18/14 | 2 | 4 | 100 | 2
2.1.1.1.12.6 | Test Cases |  | Team | Tue 2/18/14 | Tue 2/18/14 | Tue 2/18/14 | Tue 2/18/14 | 2 | 3 | 100 | 2
2.1.1.1.12.7 | Requirements Tracibility Matrix |  | Team | Tue 2/18/14 | Tue 2/18/14 | Tue 2/18/14 | Tue 2/18/14 | 2 | 2 | 100 | 2
2.1.1.1.12.8 | Acceptance Plan |  | Team | Tue 2/18/14 | Tue 2/18/14 | Tue 2/18/14 | Tue 2/18/14 | 2 | 2 | 100 | 2
2.1.1.1.12.9 | Packaging and Instalation |  | Team | Tue 2/18/14 | Tue 2/18/14 | Tue 2/18/14 | Tue 2/18/14 | 2 | 2 | 100 | 2
2.1.1.1.12.10 | Acceptance Testing |  | Team | Tue 2/18/14 | Tue 2/18/14 | Tue 2/18/14 | Tue 2/18/14 | 2 | 2 | 100 | 2
2.1.1.1.12.11 | Appendices |  | Team | Tue 2/18/14 | Tue 2/18/14 | Tue 2/18/14 | Tue 2/18/14 | 2 | 2 | 100 | 2
2.1.1.1.13 | Team Revisions |  | Team | Tue 2/18/14 | Tue 2/18/14 | Tue 2/18/14 | Tue 2/18/14 | 4 | 108 | 100 | 4
2.1.1.1.14 | Deliver Detailed Design |  | Dan | Thu 2/20/14 | Thu 2/20/14 | Thu 2/20/14 | Thu 2/20/14 | 2 | 4 | 100 | 2
2.1.1.2.1 | Introduction |  | Dan | Wed 2/12/14 | NA | Fri 2/14/14 | NA | 4 | 0 | 100 | 4
2.1.1.2.2 | Architecture Overview |  | Dan | Wed 2/12/14 | NA | Fri 2/14/14 | NA | 4 | 0 | 100 | 4
2.1.1.2.3 | Component Design |  | Tim | Wed 2/12/14 | NA | Fri 2/14/14 | NA | 4 | 1 | 100 | 4
2.1.1.2.4 | Quality Assurance |  | Tim | Wed 2/12/14 | NA | Fri 2/14/14 | NA | 4 | 0 | 100 | 4
2.1.1.2.5 | Test Plans and Procedures |  | Jesse | Wed 2/12/14 | NA | Fri 2/14/14 | NA | 4 | 0 | 100 | 4
2.1.1.2.6 | Test Cases |  | Jesse | Wed 2/12/14 | NA | Fri 2/14/14 | NA | 4 | 0 | 100 | 4
2.1.1.2.7 | Requirements Tracibility Matrix |  | Jesse | Wed 2/12/14 | NA | Fri 2/14/14 | NA | 4 | 0 | 100 | 4
2.1.1.2.8 | Acceptance Plan |  | Shawn | Wed 2/12/14 | NA | Fri 2/14/14 | NA | 4 | 0 | 100 | 4
2.1.1.2.9 | Packaging and Instalation |  | Shawn | Wed 2/12/14 | NA | Fri 2/14/14 | NA | 4 | 0 | 100 | 4
2.1.1.2.10 | Acceptance Testing |  | Shawn | Wed 2/12/14 | NA | Fri 2/14/14 | NA | 4 | 0 | 100 | 4
2.1.1.2.11 | Appendices |  | Team | Wed 2/12/14 | NA | Fri 2/14/14 | NA | 4 | 0 | 100 | 4
2.1.1.2.12.1 | Introduction |  | Tim | Fri 2/14/14 | NA | Tue 2/18/14 | NA | 2 | 0 | 100 | 2
2.1.1.2.12.2 | Architecture Overview |  | Tim | Fri 2/14/14 | NA | Tue 2/18/14 | NA | 2 | 0 | 100 | 2
2.1.1.2.12.3 | Component Design |  | Dan | Fri 2/14/14 | NA | Tue 2/18/14 | NA | 2 | 0 | 100 | 2
2.1.1.2.12.4 | Quality Assurance |  | Dan | Fri 2/14/14 | NA | Tue 2/18/14 | NA | 2 | 0 | 100 | 2
2.1.1.2.12.5 | Test Plans and Procedures |  | Shawn | Fri 2/14/14 | NA | Tue 2/18/14 | NA | 2 | 0 | 100 | 2
2.1.1.2.12.6 | Test Cases |  | Shawn | Fri 2/14/14 | NA | Tue 2/18/14 | NA | 2 | 0 | 100 | 2
2.1.1.2.12.7 | Requirements Tracibility Matrix |  | Shawn | Fri 2/14/14 | NA | Tue 2/18/14 | NA | 2 | 1 | 100 | 2
2.1.1.2.12.8 | Acceptance Plan |  | Jesse | Fri 2/14/14 | NA | Tue 2/18/14 | NA | 2 | 0 | 100 | 2
2.1.1.2.12.9 | Packaging and Instalation |  | Jesse | Fri 2/14/14 | NA | Tue 2/18/14 | NA | 2 | 0 | 100 | 2
2.1.1.2.12.10 | Acceptance Testing |  | Jesse | Fri 2/14/14 | NA | Tue 2/18/14 | NA | 2 | 0 | 100 | 2
2.1.1.2.12.11 | Appendices |  | Team | Fri 2/14/14 | NA | Tue 2/18/14 | NA | 2 | 0 | 100 | 2
2.1.1.2.13 | Team Revisions |  | Team | Thu 2/27/14 | Thu 2/27/14 | Thu 2/27/14 | Thu 2/27/14 | 2 | 1 | 100 | 2
2.1.1.2.14 | Deliver Detailed Design |  | Dan | Tue 2/18/14 | NA | Tue 2/18/14 | NA | 2 | 1 | 100 | 2
2.1.2 | Test Plan |  | Team | Thu 2/20/14 | Thu 2/20/14 | Tue 3/18/14 | NA | 100 | 44 | 100 | 100
2.2.1 | Version 0.0 |  | Team | Tue 3/18/14 | Tue 3/18/14 | Tue 4/1/14 | Tue 4/1/14 | 100 | 56 | 100 | 100
2.2.2 | Version 0.5 |  | Team | Tue 4/1/14 | Tue 4/1/14 | Tue 4/15/14 | NA | 100 | 52 | 100 | 100
2.2.3 | Version 1.0 |  | Team | Tue 3/18/14 | NA | Tue 4/1/14 | NA | 100 | 41 | 0 | 0
2.2.4 | Final Product |  | Team | Tue 4/15/14 | NA | Tue 4/29/14 | NA | 100 | 0 | 0 | 0
2.3 | Final Documetation |  | Team | Tue 4/1/14 | NA | Tue 4/29/14 | NA | 10 | 1 | 0 | 0
2.4.1 | Modify Drawings |  | Dan | Tue 1/21/14 | Tue 1/21/14 | Fri 2/21/14 | NA | 2 | 2 | 100 | 2
2.4.2 | Fix Physical Layer(Printer Control Layer) |  | Dan | Tue 1/21/14 | Tue 1/21/14 | Fri 2/21/14 | NA | 2 | 1 | 100 | 2
2.4.3 | Add Communications Layer |  | Dan | Tue 1/21/14 | Tue 1/21/14 | Fri 2/21/14 | NA | 2 | 1 | 100 | 2
2.4.4 | Team Reviews |  | Team | Mon 2/24/14 | Mon 2/24/14 | Mon 2/24/14 | Mon 2/24/14 | 4 | 1 | 100 | 4
3.1.1 | Peer Review |  |  | Wed 10/9/13 | Wed 10/9/13 | Wed 10/30/13 | Wed 10/30/13 | 4 | 2 | 100 | 4
3.1.2 | Prepare Presentations |  |  | Wed 10/9/13 | Wed 10/9/13 | Wed 10/30/13 | Wed 10/30/13 | 4 | 4 | 100 | 4
3.1.3 | SRS Gate Review |  |  | Wed 10/9/13 | Wed 10/9/13 | Fri 10/18/13 | Fri 10/18/13 | 5 | 1 | 100 | 5
3.2.1 | Peer Review |  |  | Wed 10/16/13 | Wed 10/16/13 | Wed 12/4/13 | Wed 12/4/13 | 2 | 1 | 100 | 2
3.2.2 | Prepare Presentations |  |  | Wed 10/16/13 | Wed 10/16/13 | Wed 12/4/13 | Wed 12/4/13 | 4 | 7 | 100 | 4
3.2.3 | Deliver Plan and Charter |  |  | Wed 12/4/13 | Wed 12/4/13 | Wed 12/4/13 | Wed 12/4/13 | 1 | 0 | 100 | 1
3.3.1 | Peer Review |  |  | Fri 12/6/13 | Fri 12/6/13 | Fri 12/6/13 | Fri 12/6/13 | 2 | 2 | 100 | 2
3.3.2 | Prepare Presentations |  |  | Wed 12/11/13 | Wed 12/11/13 | Wed 12/11/13 | Wed 12/11/13 | 4 | 3 | 100 | 4
3.3.3 | ADS Gate Review |  |  | Wed 12/11/13 | Wed 12/11/13 | Wed 12/11/13 | Wed 12/11/13 | 1 | 4 | 100 | 1
3.4.1 | Peer Review |  |  | Mon 2/10/14 | Mon 2/10/14 | Mon 2/10/14 | NA | 2 | 0 | 100 | 2
3.4.2 | Prepare Presentations |  |  | Wed 2/19/14 | Wed 2/19/14 | Wed 2/19/14 | Wed 2/19/14 | 4 | 11 | 100 | 4
3.4.3 | DDS Gate Review |  |  | Thu 2/20/14 | Thu 2/20/14 | Thu 2/20/14 | NA | 1 | 7 | 100 | 1
3.5.1 | Team Status Report 1 |  |  | Fri 9/13/13 | NA | Fri 9/13/13 | NA | 1 | 1 | 100 | 1
3.5.2 | Team Status Report 2 |  |  | Fri 9/27/13 | NA | Fri 9/27/13 | NA | 1 | 1 | 100 | 1
3.5.3 | Team Status Report 3 |  |  | Fri 10/11/13 | NA | Fri 10/11/13 | NA | 1 | 0 | 100 | 1
3.5.4 | Team Status Report 4 |  |  | Fri 10/25/13 | NA | Fri 10/25/13 | NA | 1 | 0 | 100 | 1
3.5.5 | Team Status Report 5 |  |  | Fri 11/8/13 | Fri 11/8/13 | Thu 11/14/13 | Thu 11/14/13 | 1 | 1 | 100 | 1
3.5.6 | Team Status Report 6 |  |  | Fri 11/22/13 | NA | Fri 11/22/13 | NA | 1 | 0 | 100 | 1
3.5.7 | Team Status Report 7 |  |  | Fri 12/6/13 | NA | Fri 12/6/13 | NA | 1 | 0 | 100 | 1
3.6.1 | Team Stauts Report SD2 1 |  |  | Thu 1/23/14 | Thu 1/23/14 | Fri 1/24/14 | Fri 1/24/14 | 1 | 1 | 100 | 1
3.6.2 | Team Stauts Report SD2 2 |  |  | Fri 2/21/14 | Fri 2/21/14 | Fri 2/21/14 | Fri 2/21/14 | 1 | 1 | 100 | 1
3.6.3 | Team Stauts Report SD2 3 |  |  | Thu 2/27/14 | Thu 2/27/14 | Fri 2/28/14 | Fri 2/28/14 | 1 | 1 | 100 | 1
3.6.4 | Team Stauts Report SD2 4 |  |  | Fri 3/28/14 | Fri 3/28/14 | Fri 3/28/14 | NA | 1 | 1 | 0 | 0
3.6.5 | Team Stauts Report SD2 5 |  |  | Fri 3/14/14 | NA | Fri 3/14/14 | NA | 1 | 0 | 0 | 0
3.6.6 | Team Stauts Report SD2 6 |  |  | Fri 3/28/14 | NA | Fri 3/28/14 | NA | 1 | 0 | 0 | 0
3.6.7 | Team Stauts Report SD2 7 |  |  | Fri 4/11/14 | Fri 4/11/14 | Fri 4/11/14 | NA | 1 | 1 | 0 | 0
3.6.8 | Team Stauts Report SD2 8 |  |  | Fri 4/25/14 | Fri 4/25/14 | Fri 4/25/14 | NA | 1 | 1 | 0 | 0
4.1.1 | Team Meeting SD1 1 |  |  | Tue 9/10/13 | Tue 9/10/13 | Tue 9/10/13 | Tue 9/10/13 | 8 | 4 | 100 | 8
4.1.2 | Team Meeting SD1 2 |  |  | Thu 9/12/13 | Thu 9/12/13 | Thu 9/12/13 | Thu 9/12/13 | 8 | 4 | 100 | 8
4.1.3 | Team Meeting SD1 3 |  |  | Tue 9/17/13 | Tue 9/17/13 | Tue 9/17/13 | Tue 9/17/13 | 8 | 4 | 100 | 8
4.1.4 | Team Meeting SD1 4 |  |  | Thu 9/19/13 | Thu 9/19/13 | Thu 9/19/13 | Thu 9/19/13 | 8 | 4 | 100 | 8
4.1.5 | Team Meeting SD1 5 |  |  | Tue 9/24/13 | Tue 9/24/13 | Tue 9/24/13 | Tue 9/24/13 | 8 | 4 | 100 | 8
4.1.6 | Team Meeting SD1 6 |  |  | Thu 9/26/13 | Thu 9/26/13 | Thu 9/26/13 | Thu 9/26/13 | 8 | 4 | 100 | 8
4.1.7 | Team Meeting SD1 7 |  |  | Tue 10/1/13 | Tue 10/1/13 | Tue 10/1/13 | Tue 10/1/13 | 8 | 4 | 100 | 8
4.1.8 | Team Meeting SD1 8 |  |  | Wed 10/2/13 | Wed 10/2/13 | Wed 10/2/13 | Wed 10/2/13 | 8 | 4 | 100 | 8
4.1.9 | Team Meeting SD1 8.5 |  |  | Sun 10/6/13 | Sun 10/6/13 | Sun 10/6/13 | Sun 10/6/13 | 8 | 4 | 100 | 8
4.1.10 | Team Meeting SD1 9 |  |  | Tue 10/8/13 | Tue 10/8/13 | Wed 10/8/14 | Wed 10/8/14 | 8 | 4 | 100 | 8
4.1.11 | Team Meeting SD1 10 |  |  | Thu 10/10/13 | Thu 10/10/13 | Fri 10/10/14 | Fri 10/10/14 | 8 | 4 | 100 | 8
4.1.12 | Team Meeting SD1 11 |  |  | Tue 10/15/13 | Tue 10/15/13 | Tue 10/15/13 | Tue 10/15/13 | 8 | 4 | 100 | 8
4.1.13 | Team Meeting SD1 12 |  |  | Fri 10/18/13 | Fri 10/18/13 | Fri 10/18/13 | Fri 10/18/13 | 8 | 4 | 100 | 8
4.1.14 | Team Meeting SD1 13 |  |  | Tue 10/22/13 | Tue 10/22/13 | Tue 10/22/13 | Tue 10/22/13 | 8 | 4 | 100 | 8
4.1.15 | Team Meeting SD1 14 |  |  | Thu 10/24/13 | Thu 10/24/13 | Thu 10/24/13 | Thu 10/24/13 | 8 | 1 | 100 | 8
4.1.16 | Team Meeting SD1 15 |  |  | Tue 10/29/13 | Tue 10/29/13 | Tue 10/29/13 | Tue 10/29/13 | 8 | 1 | 100 | 8
4.1.17 | Team Meeting SD1 16 |  |  | Sun 11/3/13 | Sun 11/3/13 | Sun 11/3/13 | Sun 11/3/13 | 8 | 5 | 100 | 8
4.1.18 | Team Meeting SD1 17 |  |  | Tue 11/5/13 | Tue 11/5/13 | Tue 11/5/13 | Tue 11/5/13 | 8 | 1 | 100 | 8
4.1.19 | Team Meeting SD1 18 |  |  | Thu 11/7/13 | Thu 11/7/13 | Thu 11/7/13 | Thu 11/7/13 | 8 | 4 | 100 | 8
4.1.20 | Team Meeting SD1 19 |  |  | Tue 11/12/13 | Tue 11/12/13 | Tue 11/12/13 | Tue 11/12/13 | 8 | 4 | 100 | 8
4.1.21 | Team Meeting SD1 20 |  |  | Thu 11/14/13 | Thu 11/14/13 | Thu 11/14/13 | Thu 11/14/13 | 8 | 4 | 100 | 8
4.1.22 | Team Meeting SD1 21 |  |  | Tue 11/19/13 | Tue 11/19/13 | Tue 11/19/13 | Tue 11/19/13 | 8 | 4 | 100 | 8
4.1.23 | Team Meeting SD1 22 |  |  | Thu 11/21/13 | Thu 11/21/13 | Thu 11/21/13 | Thu 11/21/13 | 8 | 8 | 100 | 8
4.1.24 | Team Meeting SD1 23 |  |  | Tue 11/26/13 | Tue 11/26/13 | Tue 11/26/13 | Tue 11/26/13 | 8 | 8 | 100 | 8
4.1.25 | Team Meeting SD1 24 |  |  | Thu 11/28/13 | NA | Thu 11/28/13 | NA | 8 | 0 | 100 | 8
4.1.26 | Team Meeting SD1 25 |  |  | Tue 12/3/13 | Tue 12/3/13 | Tue 12/3/13 | Tue 12/3/13 | 8 | 4 | 100 | 8
4.1.27 | Team Meeting SD1 26 |  |  | Thu 12/5/13 | Thu 12/5/13 | Thu 12/5/13 | Thu 12/5/13 | 8 | 4 | 100 | 8
4.1.28 | Team Meeting SD1 27 |  |  | Tue 12/9/14 | Tue 12/9/14 | Tue 12/9/14 | Tue 12/9/14 | 8 | 4 | 100 | 8
4.2.1 | Team Meeting SD2 1 |  |  | Tue 1/14/14 | Tue 1/14/14 | Tue 1/14/14 | Tue 1/14/14 | 8 | 8 | 100 | 8
4.2.2 | Team Meeting SD2 2 |  |  | Thu 1/16/14 | Thu 1/16/14 | Thu 1/16/14 | Thu 1/16/14 | 8 | 4 | 100 | 8
4.2.3 | Team Meeting SD2 3 |  |  | Tue 1/21/14 | Tue 1/21/14 | Tue 1/21/14 | Tue 1/21/14 | 8 | 8 | 100 | 8
4.2.4 | Team Meeting SD2 4 |  |  | Thu 1/23/14 | Thu 1/23/14 | Thu 1/23/14 | Thu 1/23/14 | 8 | 3 | 100 | 8
4.2.5 | Team Meeting SD2 5 |  |  | Tue 1/28/14 | Tue 1/28/14 | Tue 1/28/14 | Tue 1/28/14 | 8 | 4 | 100 | 8
4.2.6 | Team Meeting SD2 6 |  |  | Thu 1/30/14 | Thu 1/30/14 | Thu 1/30/14 | Thu 1/30/14 | 8 | 4 | 100 | 8
4.2.7 | Team Meeting SD2 7 |  |  | Tue 2/4/14 | Tue 2/4/14 | Tue 2/4/14 | Tue 2/4/14 | 8 | 4 | 100 | 8
4.2.8 | Team Meeting SD2 8 |  |  | Thu 2/6/14 | Thu 2/6/14 | Thu 2/6/14 | Thu 2/6/14 | 8 | 4 | 100 | 8
4.2.9 | Team Meeting SD2 9 |  |  | Tue 2/11/14 | Tue 2/11/14 | Tue 2/11/14 | Tue 2/11/14 | 8 | 4 | 100 | 8
4.2.10 | Team Meeting SD2 10 |  |  | Thu 2/13/14 | Thu 2/13/14 | Thu 2/13/14 | Thu 2/13/14 | 8 | 4 | 100 | 8
4.2.11 | Team Meeting SD2 10.1 |  |  | Sun 2/16/14 | Sun 2/16/14 | Sun 2/16/14 | Sun 2/16/14 | 8 | 6 | 100 | 8
4.2.12 | Team Meeting SD2 11 |  |  | Tue 2/18/14 | Tue 2/18/14 | Tue 2/18/14 | Tue 2/18/14 | 8 | 4 | 100 | 8
4.2.13 | Team Meeting SD2 11.1 |  |  | Wed 2/19/14 | Wed 2/19/14 | Wed 2/19/14 | Wed 2/19/14 | 8 | 4 | 100 | 8
4.2.14 | Team Meeting SD2 12 |  |  | Thu 2/20/14 | Thu 2/20/14 | Thu 2/20/14 | Thu 2/20/14 | 8 | 4 | 100 | 8
4.2.15 | Team Meeting SD2 13 |  |  | Tue 2/25/14 | Tue 2/25/14 | Tue 2/25/14 | Tue 2/25/14 | 8 | 4 | 100 | 8
4.2.16 | Team Meeting SD2 14 |  |  | Thu 2/27/14 | Thu 2/27/14 | Thu 2/27/14 | Thu 2/27/14 | 8 | 4 | 100 | 8
4.2.17 | Team Meeting SD2 15 |  |  | Tue 3/4/14 | Tue 3/4/14 | Tue 3/4/14 | Tue 3/4/14 | 8 | 2 | 100 | 8
4.2.18 | Team Meeting SD2 16 |  |  | Sun 3/9/14 | Sun 3/9/14 | Sun 3/9/14 | Sun 3/9/14 | 8 | 3 | 100 | 8
4.2.19 | Team Meeting SD2 17 |  |  | Tue 3/11/14 | NA | Tue 3/11/14 | NA | 8 | 0 | 100 | 8
4.2.20 | Team Meeting SD2 18 |  |  | Thu 3/13/14 | Thu 3/13/14 | Thu 3/13/14 | Thu 3/13/14 | 8 | 4 | 100 | 8
4.2.21 | Team Meeting SD2 19 |  |  | Sun 3/16/14 | Sun 3/16/14 | Sun 3/16/14 | Sun 3/16/14 | 8 | 10 | 100 | 8
4.2.22 | Team Meeting SD2 20 |  |  | Thu 3/20/14 | Thu 3/20/14 | Thu 3/20/14 | Thu 3/20/14 | 8 | 3 | 100 | 8
4.2.23 | Team Meeting SD2 21 |  |  | Tue 3/25/14 | Tue 3/25/14 | Tue 3/25/14 | Tue 3/25/14 | 8 | 3 | 100 | 8
4.2.24 | Team Meeting SD2 22 |  |  | Thu 3/27/14 | Thu 3/27/14 | Thu 3/27/14 | NA | 8 | 0 | 100 | 8
4.2.25 | Team Meeting SD2 23 |  |  | Tue 4/1/14 | Tue 4/1/14 | Tue 4/1/14 | Tue 4/1/14 | 8 | 1 | 100 | 8
4.2.26 | Team Meeting SD2 24 |  |  | Thu 4/3/14 | Thu 4/3/14 | Thu 4/3/14 | Thu 4/3/14 | 8 | 1 | 100 | 8
4.2.27 | Team Meeting SD2 25 |  |  | Tue 4/8/14 | Tue 4/8/14 | Tue 4/8/14 | Tue 4/8/14 | 8 | 1 | 100 | 8
4.2.28 | Team Meeting SD2 26 |  |  | Thu 4/10/14 | Thu 4/10/14 | Thu 4/10/14 | Thu 4/10/14 | 8 | 1 | 100 | 8
4.2.29 | Team Meeting SD2 27 |  |  | Tue 4/15/14 | Tue 4/15/14 | Tue 4/15/14 | Tue 4/15/14 | 8 | 4 | 100 | 8
4.2.30 | Team Meeting SD2 28 |  |  | Thu 4/17/14 | Thu 4/17/14 | Thu 4/17/14 | Thu 4/17/14 | 8 | 4 | 100 | 8
4.2.31 | Team Meeting SD2 29 |  |  | Tue 4/22/14 | Tue 4/22/14 | Tue 4/22/14 | Tue 4/22/14 | 8 | 4 | 100 | 8
4.2.32 | Team Meeting SD2 30 |  |  | Thu 4/24/14 | Thu 4/24/14 | Thu 4/24/14 | Thu 4/24/14 | 8 | 4 | 100 | 8
4.2.33 | Team Meeting SD2 31 |  |  | Tue 4/29/14 | NA | Tue 4/29/14 | NA | 8 | 2 | 100 | 8
4.2.34 | Team Meeting SD2 32 |  |  | Thu 5/1/14 | NA | Thu 5/1/14 | NA | 8 | 0 | 0 | 0
5 | Sponser Meetings |  |  | Mon 9/9/13 | Mon 9/9/13 | Tue 9/9/14 | NA | 30 | 34 | 0 | 0
6.1.1 | First Draft |  | Dan | Sun 9/29/13 | Sun 9/29/13 | Thu 10/23/14 | Thu 10/23/14 | 10 | 10 | 100 | 10
6.1.2 | Final Draft |  | Dan | Tue 12/3/13 | Tue 12/3/13 | Tue 12/3/13 | Tue 12/3/13 | 10 | 12 | 100 | 10
6.2.1 | First Draft |  | Dan | Thu 1/23/14 | Thu 1/23/14 |  | NA | 10 | 8 | 0 | 0
6.2.2 | Final Draft |  | Dan |  | NA |  | NA | 10 | 2 | 0 | 0

## Planned Hours
Planned Start | Planned Hours
2013-09-09 | 42
2013-09-10 | 50
2013-09-11 | 53
2013-09-12 | 61
2013-09-13 | 62
2013-09-17 | 66
2013-09-17 | 74
2013-09-19 | 76
2013-09-19 | 84
2013-09-24 | 116
2013-09-24 | 124
2013-09-26 | 132
2013-09-27 | 133
2013-09-29 | 143
2013-10-01 | 151
2013-10-02 | 159
2013-10-03 | 171
2013-10-03 | 199
2013-10-05 | 212
2013-10-05 | 221
2013-10-05 | 227
2013-10-06 | 235
2013-10-07 | 236
2013-10-08 | 244
2013-10-09 | 245
2013-10-09 | 258
2013-10-10 | 270
2013-10-10 | 278
2013-10-11 | 279
2013-10-13 | 281
2013-10-15 | 289
2013-10-16 | 295
2013-10-17 | 319
2013-10-18 | 327
2013-10-22 | 335
2013-10-24 | 337
2013-10-24 | 345
2013-10-25 | 346
2013-10-29 | 354
2013-10-30 | 414
2013-11-01 | 440
2013-11-01 | 454
2013-11-03 | 462
2013-11-04 | 463
2013-11-05 | 469
2013-11-05 | 477
2013-11-07 | 485
2013-11-08 | 486
2013-11-12 | 494
2013-11-14 | 502
2013-11-19 | 510
2013-11-21 | 518
2013-11-22 | 519
2013-11-26 | 527
2013-11-28 | 535
2013-11-29 | 553
2013-11-29 | 562
2013-12-03 | 571
2013-12-03 | 574
2013-12-03 | 582
2013-12-03 | 592
2013-12-04 | 593
2013-12-05 | 596
2013-12-05 | 604
2013-12-06 | 606
2013-12-06 | 607
2013-12-09 | 610
2013-12-10 | 613
2013-12-11 | 616
2013-12-11 | 621
2014-01-14 | 629
2014-01-15 | 632
2014-01-16 | 640
2014-01-20 | 643
2014-01-21 | 687
2014-01-21 | 693
2014-01-21 | 701
2014-01-23 | 702
2014-01-23 | 710
2014-01-23 | 720
2014-01-28 | 728
2014-01-30 | 736
2014-02-04 | 744
2014-02-06 | 752
2014-02-10 | 754
2014-02-11 | 762
2014-02-12 | 806
2014-02-13 | 814
2014-02-14 | 836
2014-02-16 | 844
2014-02-18 | 870
2014-02-18 | 872
2014-02-18 | 880
2014-02-19 | 884
2014-02-19 | 892
2014-02-20 | 894
2014-02-20 | 994
2014-02-20 | 995
2014-02-20 | 1003
2014-02-21 | 1004
2014-02-24 | 1008
2014-02-25 | 1016
2014-02-27 | 1018
2014-02-27 | 1019
2014-02-27 | 1027
2014-03-04 | 1035
2014-03-09 | 1043
2014-03-11 | 1051
2014-03-13 | 1059
2014-03-14 | 1060
2014-03-16 | 1068
2014-03-18 | 1168
2014-03-18 | 1268
2014-03-20 | 1276
2014-03-25 | 1284
2014-03-27 | 1292
2014-03-28 | 1293
2014-03-28 | 1294
2014-04-01 | 1394
2014-04-01 | 1404
2014-04-01 | 1412
2014-04-03 | 1420
2014-04-08 | 1428
2014-04-10 | 1436
2014-04-11 | 1437
2014-04-15 | 1537
2014-04-15 | 1545
2014-04-17 | 1553
2014-04-22 | 1561
2014-04-24 | 1569
2014-04-25 | 1570
2014-04-29 | 1578
2014-05-01 | 1586

## Actual
Planned Start | Actual Work Hours
2013-09-09 | 38.5
2013-09-10 | 42.5
2013-09-11 | 45.5
2013-09-12 | 49.5
2013-09-13 | 50.5
2013-09-17 | 54.5
2013-09-17 | 58.5
2013-09-19 | 60.5
2013-09-19 | 64.5
2013-09-24 | 81
2013-09-24 | 85
2013-09-26 | 89
2013-09-27 | 90
2013-09-29 | 100
2013-10-01 | 104
2013-10-02 | 108
2013-10-03 | 125
2013-10-03 | 150
2013-10-05 | 168
2013-10-05 | 170
2013-10-05 | 178
2013-10-06 | 182
2013-10-07 | 182
2013-10-08 | 186
2013-10-09 | 186
2013-10-09 | 193
2013-10-10 | 201
2013-10-10 | 205
2013-10-11 | 205
2013-10-13 | 205
2013-10-15 | 209
2013-10-16 | 217
2013-10-17 | 229
2013-10-18 | 233
2013-10-22 | 237
2013-10-24 | 237
2013-10-24 | 238
2013-10-25 | 238
2013-10-29 | 239
2013-10-30 | 266
2013-11-01 | 284
2013-11-01 | 291
2013-11-03 | 296
2013-11-04 | 297
2013-11-05 | 304
2013-11-05 | 305
2013-11-07 | 309
2013-11-08 | 310
2013-11-12 | 314
2013-11-14 | 318
2013-11-19 | 322
2013-11-21 | 330
2013-11-22 | 330
2013-11-26 | 338
2013-11-28 | 338
2013-11-29 | 344
2013-11-29 | 347
2013-12-03 | 351
2013-12-03 | 351
2013-12-03 | 355
2013-12-03 | 367
2013-12-04 | 367
2013-12-05 | 370
2013-12-05 | 374
2013-12-06 | 376
2013-12-06 | 376
2013-12-09 | 377
2013-12-10 | 379
2013-12-11 | 380
2013-12-11 | 387
2014-01-14 | 395
2014-01-15 | 397
2014-01-16 | 401
2014-01-20 | 405
2014-01-21 | 474
2014-01-21 | 478
2014-01-21 | 486
2014-01-23 | 487
2014-01-23 | 490
2014-01-23 | 498
2014-01-28 | 502
2014-01-30 | 506
2014-02-04 | 510
2014-02-06 | 514
2014-02-10 | 514
2014-02-11 | 518
2014-02-12 | 519
2014-02-13 | 523
2014-02-14 | 524
2014-02-16 | 530
2014-02-18 | 665
2014-02-18 | 666
2014-02-18 | 670
2014-02-19 | 681
2014-02-19 | 685
2014-02-20 | 689
2014-02-20 | 733
2014-02-20 | 740
2014-02-20 | 744
2014-02-21 | 745
2014-02-24 | 746
2014-02-25 | 750
2014-02-27 | 751
2014-02-27 | 752
2014-02-27 | 756
2014-03-04 | 758
2014-03-09 | 761
2014-03-11 | 761
2014-03-13 | 765
2014-03-14 | 765
2014-03-16 | 775
2014-03-18 | 831
2014-03-18 | 872
2014-03-20 | 875
2014-03-25 | 878
2014-03-27 | 878
2014-03-28 | 879
2014-03-28 | 879
2014-04-01 | 931
2014-04-01 | 932
2014-04-01 | 933
2014-04-03 | 934
2014-04-08 | 935
2014-04-10 | 936
2014-04-11 | 937
2014-04-15 | 937
2014-04-15 | 941
2014-04-17 | 945
2014-04-22 | 949
2014-04-24 | 953
2014-04-25 | 954
2014-04-29 | 956
2014-05-01 | 956

## earned
Planned Finish | Earned Vaule
2013-09-09 | 30
2013-09-10 | 38
2013-09-11 | 41
2013-09-12 | 49
2013-09-13 | 50
2013-09-17 | 58
2013-09-19 | 62
2013-09-19 | 70
2013-09-24 | 72
2013-09-24 | 80
2013-09-26 | 88
2013-09-27 | 89
2013-10-01 | 97
2013-10-02 | 105
2013-10-03 | 149
2013-10-05 | 157
2013-10-06 | 160
2013-10-06 | 168
2013-10-08 | 169
2013-10-08 | 177
2013-10-09 | 179
2013-10-10 | 207
2013-10-10 | 215
2013-10-11 | 216
2013-10-13 | 230
2013-10-15 | 238
2013-10-18 | 243
2013-10-18 | 251
2013-10-22 | 259
2013-10-23 | 269
2013-10-24 | 271
2013-10-24 | 279
2013-10-25 | 280
2013-10-29 | 288
2013-10-30 | 291
2013-10-30 | 299
2013-11-01 | 301
2013-11-03 | 309
2013-11-04 | 326
2013-11-04 | 353
2013-11-05 | 355
2013-11-05 | 363
2013-11-07 | 371
2013-11-12 | 379
2013-11-14 | 380
2013-11-14 | 388
2013-11-18 | 415
2013-11-19 | 423
2013-11-20 | 426
2013-11-21 | 434
2013-11-22 | 435
2013-11-26 | 443
2013-11-28 | 451
2013-11-29 | 464
2013-11-29 | 490
2013-11-29 | 516
2013-12-03 | 524
2013-12-03 | 533
2013-12-03 | 561
2013-12-04 | 568
2013-12-05 | 576
2013-12-06 | 577
2013-12-06 | 579
2013-12-09 | 582
2013-12-09 | 590
2013-12-11 | 595
2014-01-14 | 603
2014-01-15 | 615
2014-01-16 | 623
2014-01-18 | 638
2014-01-20 | 641
2014-01-21 | 649
2014-01-23 | 657
2014-01-24 | 658
2014-01-28 | 666
2014-01-30 | 674
2014-02-04 | 682
2014-02-06 | 690
2014-02-10 | 692
2014-02-11 | 700
2014-02-13 | 708
2014-02-14 | 752
2014-02-16 | 760
2014-02-18 | 762
2014-02-18 | 770
2014-02-18 | 792
2014-02-18 | 862
2014-02-19 | 866
2014-02-19 | 874
2014-02-20 | 875
2014-02-20 | 877
2014-02-20 | 885
2014-02-21 | 886
2014-02-21 | 892
2014-02-24 | 896
2014-02-25 | 904
2014-02-27 | 906
2014-02-27 | 914
2014-02-28 | 915
2014-03-04 | 923
2014-03-09 | 931
2014-03-11 | 939
2014-03-13 | 947
2014-03-14 | 948
2014-03-16 | 956
2014-03-18 | 1056
2014-03-20 | 1064
2014-03-25 | 1072
2014-03-27 | 1080
2014-03-28 | 1081
2014-03-28 | 1082
2014-04-01 | 1182
2014-04-01 | 1190
2014-04-01 | 1290
2014-04-03 | 1298
2014-04-08 | 1306
2014-04-10 | 1314
2014-04-11 | 1315
2014-04-15 | 1323
2014-04-15 | 1423
2014-04-17 | 1431
2014-04-22 | 1439
2014-04-24 | 1447
2014-04-25 | 1448
2014-04-29 | 1558
2014-04-29 | 1566
2014-05-01 | 1574

## Total
Date | Planned | Actual | Earned Value
2013-09-11 | 53 | 45.5 | 41
2013-09-12 | 61 | 49.5 | 49
2013-09-13 | 62 | 50.5 | 50
2013-09-17 | 66 | 54.5 | 58
2013-09-19 | 76 | 60.5 | 62
2013-09-24 | 116 | 81 | 72
2013-09-26 | 132 | 89 | 88
2013-09-27 | 133 | 90 | 89
2013-09-29 | 143 | 100 | 89
2013-10-01 | 151 | 104 | 97
2013-10-02 | 159 | 108 | 105
2013-10-03 | 171 | 125 | 149
2013-10-05 | 212 | 168 | 157
2013-10-06 | 235 | 182 | 160
2013-10-07 | 236 | 182 | 160
2013-10-08 | 244 | 186 | 169
2013-10-09 | 245 | 186 | 179
2013-10-10 | 270 | 201 | 207
2013-10-11 | 279 | 205 | 216
2013-10-13 | 281 | 205 | 230
2013-10-15 | 289 | 209 | 238
2013-10-16 | 295 | 217 | 238
2013-10-17 | 319 | 229 | 238
2013-10-18 | 327 | 233 | 243
2013-10-22 | 335 | 237 | 259
2013-10-23 | 335 | 237 | 269
2013-10-24 | 337 | 237 | 271
2013-10-25 | 346 | 238 | 280
2013-10-29 | 354 | 239 | 288
2013-10-30 | 414 | 266 | 291
2013-11-01 | 440 | 284 | 301
2013-11-03 | 462 | 296 | 309
2013-11-04 | 463 | 297 | 326
2013-11-05 | 469 | 304 | 355
2013-11-07 | 485 | 309 | 371
2013-11-08 | 486 | 310 | 371
2013-11-12 | 494 | 314 | 379
2013-11-14 | 502 | 318 | 380
2013-11-18 | 502 | 318 | 415
2013-11-19 | 510 | 322 | 423
2013-11-20 | 510 | 322 | 426
2013-11-21 | 518 | 330 | 434
2013-11-22 | 519 | 330 | 435
2013-11-26 | 527 | 338 | 443
2013-11-28 | 535 | 338 | 451
2013-11-29 | 553 | 344 | 464
2013-12-03 | 571 | 351 | 524
2013-12-04 | 593 | 367 | 568
2013-12-05 | 596 | 370 | 576
2013-12-06 | 606 | 376 | 577
2013-12-09 | 610 | 377 | 582
2013-12-10 | 613 | 379 | 582
2013-12-11 | 616 | 380 | 595
2014-01-14 | 629 | 395 | 603
2014-01-15 | 632 | 397 | 615
2014-01-16 | 640 | 401 | 623
2014-01-18 | 640 | 401 | 638
2014-01-20 | 643 | 405 | 641
2014-01-21 | 687 | 474 | 649
2014-01-23 | 702 | 487 | 657
2014-01-24 | 702 | 487 | 658
2014-01-28 | 728 | 502 | 666
2014-01-30 | 736 | 506 | 674
2014-02-04 | 744 | 510 | 682
2014-02-06 | 752 | 514 | 690
2014-02-10 | 754 | 514 | 692
2014-02-11 | 762 | 518 | 700
2014-02-12 | 806 | 519 | 700
2014-02-13 | 814 | 523 | 708
2014-02-14 | 836 | 524 | 752
2014-02-16 | 844 | 530 | 760
2014-02-18 | 870 | 665 | 762
2014-02-19 | 884 | 681 | 866
2014-02-20 | 894 | 689 | 875
2014-02-21 | 1004 | 745 | 886
2014-02-24 | 1008 | 746 | 896
2014-02-25 | 1016 | 750 | 904
2014-02-27 | 1018 | 751 | 906
2014-02-28 | 1018 | 751 | 915
2014-03-04 | 1035 | 758 | 923
2014-03-09 | 1043 | 761 | 931
2014-03-11 | 1051 | 761 | 939
2014-03-13 | 1059 | 765 | 947
2014-03-14 | 1060 | 765 | 948
2014-03-16 | 1068 | 775 | 956
2014-03-18 | 1168 | 831 | 1056
2014-03-20 | 1276 | 875 | 1064
2014-03-25 | 1284 | 878 | 1072
2014-03-27 | 1292 | 878 | 1080
2014-03-28 | 1293 | 879 | 1081
2014-04-01 | 1394 | 931 | 1182
2014-04-03 | 1420 | 934 | 1298
2014-04-08 | 1428 | 935 | 1306
2014-04-10 | 1436 | 936 | 1314
2014-04-11 | 1437 | 937 | 1315
2014-04-15 | 1537 | 980 | 1323
2014-04-17 | 1553 | 1000 | 1431
2014-04-22 | 1561 | 1020 | 1439
2014-04-24 | 1569 | 1040 | 1447
2014-04-25 | 1570 | 1160 | 1448
2014-04-29 | 1578 | 1180 | 1558
2014-05-01 | 1586 | 1250 | 1574