## Sheet1
Task Mode | Task Number | Task Name | Predecessors | Resource Initials | Planned Start | Actual Start | Planned Finish | Actual Finish | Planned Work Hours | Actual Work Hours | % Work Completed | Earned Vaule | CPI (Calc) | SPI (Calc)
Manually Scheduled | 4.1.1 | Team Meeting SD1 1 |  |  | Tue 9/10/13 | Tue 9/10/13 | Tue 9/10/13 | Tue 9/10/13 | 8 | 4 | 100 | 8 | 0 | 1
Manually Scheduled | 4.1.2 | Team Meeting SD1 2 |  |  | Thu 9/12/13 | Thu 9/12/13 | Thu 9/12/13 | Thu 9/12/13 | 8 | 4 | 100 | 8 | 0 | 1
Manually Scheduled | 4.1.3 | Team Meeting SD1 3 |  |  | Tue 9/17/13 | Tue 9/17/13 | Tue 9/17/13 | Tue 9/17/13 | 8 | 4 | 100 | 8 | 0 | 1
Manually Scheduled | 4.1.4 | Team Meeting SD1 4 |  |  | Thu 9/19/13 | Thu 9/19/13 | Thu 9/19/13 | Thu 9/19/13 | 8 | 4 | 100 | 8 | 0 | 1
Manually Scheduled | 4.1.5 | Team Meeting SD1 5 |  |  | Tue 9/24/13 | Tue 9/24/13 | Tue 9/24/13 | Tue 9/24/13 | 8 | 4 | 100 | 8 | 0 | 1
Manually Scheduled | 4.1.6 | Team Meeting SD1 6 |  |  | Thu 9/26/13 | Thu 9/26/13 | Thu 9/26/13 | Thu 9/26/13 | 8 | 4 | 100 | 8 | 0 | 1
Manually Scheduled | 4.1.7 | Team Meeting SD1 7 |  |  | Tue 10/1/13 | Tue 10/1/13 | Tue 10/1/13 | Tue 10/1/13 | 8 | 4 | 100 | 8 | 0 | 1
Manually Scheduled | 4.1.8 | Team Meeting SD1 8 |  |  | Wed 10/2/13 | Wed 10/2/13 | Wed 10/2/13 | Wed 10/2/13 | 8 | 4 | 100 | 8 | 0 | 1
Manually Scheduled | 4.1.9 | Team Meeting SD1 8.5 |  |  | Sun 10/6/13 | Sun 10/6/13 | Sun 10/6/13 | Sun 10/6/13 | 8 | 4 | 100 | 8 | 0 | 1
Manually Scheduled | 4.1.10 | Team Meeting SD1 9 |  |  | Tue 10/8/13 | Tue 10/8/13 | Tue 10/8/13 | NA | 8 | 4 | 100 | 8 | 0 | 1
Manually Scheduled | 4.1.11 | Team Meeting SD1 10 |  |  | Thu 10/10/13 | Thu 10/10/13 | Thu 10/10/13 | NA | 8 | 4 | 100 | 8 | 0 | 1
Manually Scheduled | 4.1.12 | Team Meeting SD1 11 |  |  | Tue 10/15/13 | Tue 10/15/13 | Tue 10/15/13 | NA | 8 | 4 | 100 | 8 | 0 | 1
Manually Scheduled | 4.1.13 | Team Meeting SD1 12 |  |  | Fri 10/18/13 | Fri 10/18/13 | Fri 10/18/13 | NA | 8 | 4 | 100 | 8 | 0 | 1
Manually Scheduled | 4.1.14 | Team Meeting SD1 13 |  |  | Tue 10/22/13 | Tue 10/22/13 | Tue 10/22/13 | NA | 8 | 4 | 100 | 8 | 0 | 1
Manually Scheduled | 4.1.15 | Team Meeting SD1 14 |  |  | Thu 10/24/13 | Thu 10/24/13 | Thu 10/24/13 | NA | 8 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 1.1.1.1.1 | Meet with Sponser |  | Dan,Jesse,Tim | Wed 9/11/13 | Wed 9/11/13 | Wed 9/11/13 | Wed 9/11/13 | 3 | 3 | 100 | 3 | 1 | 1
Manually Scheduled | 1.1.1.1.2 | Derive Requirements |  | Team | Tue 9/17/13 | Tue 9/17/13 | Thu 9/19/13 | Thu 9/19/13 | 3 | 3 | 100 | 3 | 1 | 1
Manually Scheduled | 1.1.1.1.3 | Product Concept |  | Dan | Tue 9/17/13 | Tue 9/17/13 | Thu 9/19/13 | Thu 9/19/13 | 1 | 1 | 100 | 1 | 1 | 1
Manually Scheduled | 1.1.1.1.4 | Product Description & Functional Overview |  | Jesse | Thu 9/19/13 | Thu 9/19/13 | Tue 9/24/13 | Tue 9/24/13 | 2 | 2 | 100 | 2 | 1 | 1
Manually Scheduled | 1.1.1.1.5 | Customer Requirements | 6 | Jesse,Shawn,Tim | Tue 9/24/13 | Tue 9/24/13 | Thu 10/3/13 | Thu 10/3/13 | 4 | 5.5 | 100 | 4 | 0 | 1
Manually Scheduled | 1.1.1.1.6 | Packaging Requirements | 6 | Tim | Tue 9/24/13 | Tue 9/24/13 | Thu 10/3/13 | Thu 10/3/13 | 4 | 1 | 100 | 4 | 0 | 1
Manually Scheduled | 1.1.1.1.7 | Performance Requirements | 6 | Tim | Tue 9/24/13 | Tue 9/24/13 | Thu 10/3/13 | Thu 10/3/13 | 4 | 1 | 100 | 4 | 0 | 1
Manually Scheduled | 1.1.1.1.8 | Saftey Requirements | 6 | Tim | Tue 9/24/13 | Tue 9/24/13 | Thu 10/3/13 | Thu 10/3/13 | 4 | 1 | 100 | 4 | 0 | 1
Manually Scheduled | 1.1.1.1.9 | Maintenance & Support Requirements | 6 | Shawn | Tue 9/24/13 | Tue 9/24/13 | Thu 10/3/13 | Thu 10/3/13 | 4 | 1 | 100 | 4 | 0 | 1
Manually Scheduled | 1.1.1.1.10 | Other Requirements | 6 | Tim | Tue 9/24/13 | Tue 9/24/13 | Thu 10/3/13 | Thu 10/3/13 | 4 | 1 | 100 | 4 | 0 | 1
Auto Scheduled | 1.1.1.1.11 | Acceptance Criteria | 9,10,11,12,13,14 | Dan | Tue 9/24/13 | Tue 9/24/13 | Thu 10/3/13 | Thu 10/3/13 | 2 | 1 | 100 | 2 | 0 | 1
Manually Scheduled | 1.1.1.1.12 | Use Cases | 6 | Jesse | Tue 9/24/13 | Tue 9/24/13 | Thu 10/3/13 | Thu 10/3/13 | 2 | 1 | 100 | 2 | 0 | 1
Manually Scheduled | 1.1.1.1.13 | Feasibility Assessment | 6 | Tim,Shawn,Jesse | Tue 9/24/13 | Tue 9/24/13 | Thu 10/3/13 | Thu 10/3/13 | 2 | 3 | 100 | 2 | 0 | 1
Manually Scheduled | 1.1.1.1.14 | Future Items |  | Tim | Tue 9/24/13 | Tue 9/24/13 | Thu 10/3/13 | Thu 10/3/13 | 2 | 1 | 100 | 2 | 0 | 1
Manually Scheduled | 1.1.1.1.15 | Rough Draft Compliation |  | Dan | Thu 10/3/13 | Thu 10/3/13 | Thu 10/3/13 | Thu 10/3/13 | 12 | 17 | 100 | 12 | 0 | 1
Manually Scheduled | 1.1.1.1.16.1 | Product Concept |  | Jesse | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | 1 | 1 | 100 | 1 | 1 | 1
Manually Scheduled | 1.1.1.1.16.2 | Product Description & Functional Overview |  | Tim | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | 1 | 1 | 100 | 1 | 1 | 1
Manually Scheduled | 1.1.1.1.16.3 | Customer Requirements |  | Dan | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | 1 | 1 | 100 | 1 | 0 | 1
Manually Scheduled | 1.1.1.1.16.4 | Packaging Requirements |  | Dan | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | 1 | 1 | 100 | 1 | 0 | 1
Manually Scheduled | 1.1.1.1.16.5 | Performance Requirements |  | Dan | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | 1 | 1 | 100 | 1 | 0 | 1
Manually Scheduled | 1.1.1.1.16.6 | Saftey Requirements |  | Dan | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | 1 | 1 | 100 | 1 | 0 | 1
Manually Scheduled | 1.1.1.1.16.7 | Maintenance & Support Requirements |  | Dan | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | 1 | 1 | 100 | 1 | 0 | 1
Manually Scheduled | 1.1.1.1.16.8 | Other Requirements |  | Dan | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | Sat 10/5/13 | 1 | 1 | 100 | 1 | 0 | 1
Auto Scheduled | 1.1.1.1.16.9 | Acceptance Criteria |  | Shawn | Sat 10/5/13 | Sat 10/5/13 | Sun 10/6/13 | Sun 10/6/13 | 1 | 1 | 100 | 1 | 0 | 1
Manually Scheduled | 1.1.1.1.16.10 | Use Cases |  | Tim | Sat 10/5/13 | Sat 10/5/13 | Sun 10/6/13 | Sun 10/6/13 | 1 | 2 | 100 | 1 | 0 | 1
Manually Scheduled | 1.1.1.1.16.11 | Feasibility Assessment |  | Jesse,Shawn | Sat 10/5/13 | Sat 10/5/13 | Sun 10/6/13 | Sun 10/6/13 | 1 | 5 | 100 | 1 | 0 | 1
Manually Scheduled | 1.1.1.1.16.12 | Future Items |  | Shawn | Sat 10/5/13 | Sat 10/5/13 | Tue 10/8/13 | Tue 10/8/13 | 1 | 1 | 100 | 1 | 0 | 1
Manually Scheduled | 1.1.1.1.17 | Team Revisions |  |  | Sat 10/5/13 | Sat 10/5/13 | Wed 10/9/13 | Wed 10/9/13 | 1 | 1 | 100 | 1 | 0 | 1
Manually Scheduled | 1.1.1.1.19.1 | Derive Requirements |  | Team | Sat 10/5/13 | Sat 10/5/13 | Mon 11/4/13 | NA | 1 | 0 | 0 | 0 | 1 | 0
Manually Scheduled | 1.1.1.1.19.2 | Product Concept |  | Dan | Sat 10/5/13 | Sat 10/5/13 | Mon 11/4/13 | NA | 1 | 0 | 0 | 0 | 1 | 0
Manually Scheduled | 1.1.1.1.19.3 | Product Description & Functional Overview |  | Jesse | Sat 10/5/13 | Sat 10/5/13 | Mon 11/4/13 | NA | 1 | 0 | 0 | 0 | 1 | 0
Manually Scheduled | 1.1.1.1.19.4 | Customer Requirements |  | Jesse,Shawn,Tim | Sat 10/5/13 | Sat 10/5/13 | Mon 11/4/13 | NA | 1 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 1.1.1.1.19.5 | Packaging Requirements |  | Tim | Sat 10/5/13 | Sat 10/5/13 | Mon 11/4/13 | NA | 1 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 1.1.1.1.19.6 | Performance Requirements |  | Tim | Sat 10/5/13 | Sat 10/5/13 | Mon 11/4/13 | NA | 1 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 1.1.1.1.19.7 | Saftey Requirements |  | Tim | Sat 10/5/13 | Sat 10/5/13 | Mon 11/4/13 | NA | 1 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 1.1.1.1.19.8 | Maintenance & Support Requirements |  | Shawn | Sat 10/5/13 | Sat 10/5/13 | Mon 11/4/13 | NA | 1 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 1.1.1.1.19.9 | Other Requirements |  | Tim | Sat 10/5/13 | Sat 10/5/13 | Mon 11/4/13 | NA | 1 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 1.1.1.1.19.11 | Use Cases |  | Jesse | Sat 10/5/13 | Sat 10/5/13 | Mon 11/4/13 | NA | 1 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 1.1.1.1.19.12 | Feasibility Assessment |  | Tim,Shawn,Jesse | Sat 10/5/13 | Sat 10/5/13 | Mon 11/4/13 | NA | 4 | 7 | 0 | 0 | 0 | 0
Manually Scheduled | 1.1.1.1.19.13 | Future Items |  | Tim | Sat 10/5/13 | Sat 10/5/13 | Mon 11/4/13 | NA | 1 | 0 | 0 | 0 | 0 | 0
Auto Scheduled | 1.1.1.1.19.10 | Acceptance Criteria |  | Dan | Mon 10/7/13 | NA | Mon 11/4/13 | NA | 1 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 1.1.1.1.18 | Deliver SRS |  |  | Wed 10/9/13 | Wed 10/9/13 | Wed 10/9/13 | Wed 10/9/13 | 1 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 1.1.2.1.1 | General Organization |  | Dan | Thu 10/3/13 | Thu 10/3/13 | Thu 10/10/13 | Thu 10/10/13 | 2 | 2 | 100 | 2 | 0 | 1
Manually Scheduled | 1.1.2.1.2 | Scope Statement |  | Shawn | Thu 10/3/13 | Thu 10/3/13 | Thu 10/10/13 | Thu 10/10/13 | 2 | 2 | 100 | 2 | 0 | 1
Manually Scheduled | 1.1.2.1.3 | Cost Management Plan |  | Shawn | Thu 10/3/13 | Thu 10/3/13 | Thu 10/10/13 | Thu 10/10/13 | 2 | 2 | 100 | 2 | 0 | 1
Manually Scheduled | 1.1.2.1.4 | Earned Value Management |  | Tim | Thu 10/3/13 | Thu 10/3/13 | Thu 10/10/13 | Thu 10/10/13 | 2 | 1 | 100 | 2 | 0 | 1
Manually Scheduled | 1.1.2.1.5 | Scope Management Plan |  | Tim | Thu 10/3/13 | Thu 10/3/13 | Thu 10/10/13 | Thu 10/10/13 | 2 | 2 | 100 | 2 | 0 | 1
Manually Scheduled | 1.1.2.1.6 | Work Breakdown Srtucture |  | Dan | Thu 10/3/13 | Thu 10/3/13 | Thu 10/10/13 | Thu 10/10/13 | 6 | 6 | 33.33 | 2 | 0 | 0.33
Manually Scheduled | 1.1.2.1.7 | Quality Management Plan |  | Jesse | Thu 10/3/13 | Thu 10/3/13 | Thu 10/10/13 | Thu 10/10/13 | 2 | 1 | 100 | 2 | 0 | 1
Manually Scheduled | 1.1.2.1.8 | Communication Plan |  | Jesse | Thu 10/3/13 | Thu 10/3/13 | Thu 10/10/13 | Thu 10/10/13 | 2 | 1 | 100 | 2 | 0 | 1
Manually Scheduled | 1.1.2.1.9 | Change Management Plan |  | Tim | Thu 10/3/13 | Thu 10/3/13 | Thu 10/10/13 | Thu 10/10/13 | 2 | 2 | 100 | 2 | 0 | 1
Manually Scheduled | 1.1.2.1.10 | Risk Management Plan |  | Shawn | Thu 10/3/13 | Thu 10/3/13 | Thu 10/10/13 | Thu 10/10/13 | 2 | 3 | 100 | 2 | 0 | 1
Manually Scheduled | 1.1.2.1.11 | Procurement Management Plan |  | Jesse | Thu 10/3/13 | Thu 10/3/13 | Thu 10/10/13 | Thu 10/10/13 | 2 | 2 | 100 | 2 | 0 | 1
Manually Scheduled | 1.1.2.1.12 | Project Closeout Report |  | Tim | Thu 10/3/13 | Thu 10/3/13 | Thu 10/10/13 | Thu 10/10/13 | 2 | 1 | 0 | 0 | 0 | 0
Manually Scheduled | 1.1.2.1.13.1 | General Organization |  | Tim | Thu 10/10/13 | Thu 10/10/13 | Sun 10/13/13 | Sun 10/13/13 | 1 | 1 | 100 | 1 | 0 | 1
Manually Scheduled | 1.1.2.1.13.2 | Scope Statement |  | Jesse | Thu 10/10/13 | Thu 10/10/13 | Sun 10/13/13 | Sun 10/13/13 | 1 | 1 | 100 | 1 | 0 | 1
Manually Scheduled | 1.1.2.1.13.3 | Cost Management Plan |  | Dan | Thu 10/10/13 | Thu 10/10/13 | Sun 10/13/13 | Sun 10/13/13 | 1 | 1 | 100 | 1 | 0 | 1
Manually Scheduled | 1.1.2.1.13.4 | Earned Value Management |  | Shawn | Thu 10/10/13 | Thu 10/10/13 | Sun 10/13/13 | Sun 10/13/13 | 1 | 1 | 100 | 1 | 0 | 1
Manually Scheduled | 1.1.2.1.13.5 | Scope Management Plan |  | Jesse | Thu 10/10/13 | Thu 10/10/13 | Sun 10/13/13 | Sun 10/13/13 | 1 | 1 | 100 | 1 | 0 | 1
Manually Scheduled | 1.1.2.1.13.6 | Work Breakdown Srtucture |  | Tim | Thu 10/10/13 | Thu 10/10/13 | Sun 10/13/13 | Sun 10/13/13 | 1 | 1 | 100 | 1 | 0 | 1
Manually Scheduled | 1.1.2.1.13.7 | Quality Management Plan |  | Dan | Thu 10/10/13 | Thu 10/10/13 | Sun 10/13/13 | Sun 10/13/13 | 1 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 1.1.2.1.13.8 | Communication Plan |  | Shawn | Thu 10/10/13 | Thu 10/10/13 | Sun 10/13/13 | Sun 10/13/13 | 1 | 1 | 0 | 0 | 0 | 0
Manually Scheduled | 1.1.2.1.13.9 | Change Management Plan |  | Jesse | Thu 10/10/13 | Thu 10/10/13 | Sun 10/13/13 | Sun 10/13/13 | 1 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 1.1.2.1.13.10 | Risk Management Plan |  | Tim | Thu 10/10/13 | Thu 10/10/13 | Sun 10/13/13 | Sun 10/13/13 | 1 | 1 | 100 | 1 | 0 | 1
Manually Scheduled | 1.1.2.1.13.11 | Procurement Management Plan |  | Shawn | Thu 10/10/13 | Thu 10/10/13 | Sun 10/13/13 | Sun 10/13/13 | 1 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 1.1.2.1.13.12 | Project Closeout Report |  | Dan | Thu 10/10/13 | Thu 10/10/13 | Sun 10/13/13 | Sun 10/13/13 | 1 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 1.1.2.1.14 | Team Changes |  |  | Sun 10/13/13 | Sun 10/13/13 | Sun 10/13/13 | Sun 10/13/13 | 2 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 1.1.2.1.15 | First Draft Charter |  |  | Thu 10/24/13 | Thu 10/24/13 | Thu 10/24/13 | Thu 10/24/13 | 2 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 1.1.2.2.1 | General Organization |  |  | Thu 10/17/13 | NA | Thu 10/31/13 | NA | 2 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 1.1.2.2.2 | Scope Statement |  |  | Thu 10/17/13 | NA | Thu 10/31/13 | NA | 2 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 1.1.2.2.3 | Cost Management Plan |  |  | Thu 10/17/13 | NA | Thu 10/31/13 | NA | 2 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 1.1.2.2.4 | Earned Value Management |  |  | Thu 10/17/13 | NA | Thu 10/31/13 | NA | 2 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 1.1.2.2.5 | Scope Management Plan |  |  | Thu 10/17/13 | NA | Thu 10/31/13 | NA | 2 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 1.1.2.2.6 | Work Breakdown Srtucture |  |  | Thu 10/17/13 | NA | Thu 10/31/13 | NA | 2 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 1.1.2.2.7 | Quality Management Plan |  |  | Thu 10/17/13 | NA | Thu 10/31/13 | NA | 2 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 1.1.2.2.8 | Communication Plan |  |  | Thu 10/17/13 | NA | Thu 10/31/13 | NA | 2 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 1.1.2.2.9 | Change Management Plan |  |  | Thu 10/17/13 | NA | Thu 10/31/13 | NA | 2 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 1.1.2.2.10 | Risk Management Plan |  |  | Thu 10/17/13 | NA | Thu 10/31/13 | NA | 2 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 1.1.2.2.11 | Procurement Management Plan |  |  | Thu 10/17/13 | NA | Thu 10/31/13 | NA | 2 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 1.1.2.2.12 | Project Closeout Report |  |  | Thu 10/17/13 | NA | Thu 10/31/13 | NA | 2 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 3.4.1 | Team Status Report 1 |  |  | Fri 9/13/13 | NA | Fri 9/13/13 | NA | 1 | 1 | 100 | 1 | 0 | 1
Manually Scheduled | 3.4.2 | Team Status Report 2 |  |  | Fri 9/27/13 | NA | Fri 9/27/13 | NA | 1 | 1 | 100 | 1 | 0 | 1
Manually Scheduled | 3.4.3 | Team Status Report 3 |  |  | Fri 10/11/13 | NA | Fri 10/11/13 | NA | 1 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 3.4.4 | Team Status Report 4 |  |  | Fri 10/25/13 | NA | Fri 10/25/13 | NA | 1 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 3.4.5 | Team Status Report 5 |  |  | Fri 11/8/13 | NA | Fri 11/8/13 | NA | 1 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 3.4.6 | Team Status Report 6 |  |  | Fri 11/22/13 | NA | Fri 11/22/13 | NA | 1 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 3.4.7 | Team Status Report 7 |  |  | Fri 12/6/13 | NA | Fri 12/6/13 | NA | 1 | 0 | 0 | 0 | 0 | 0
Manually Scheduled | 6.1.1 | First Draft |  |  | Sun 9/29/13 | Sun 9/29/13 | Wed 10/23/13 | NA | 10 | 10 | 100 | 10 | 0 | 1
Manually Scheduled | 6.1.2 | Final Draft |  |  | Wed 10/23/13 | NA | Wed 12/4/13 | NA | 10 | 0 | 0 | 0 | 0 | 0
[9 empty] | 298 | 168.5 |  | 219 | 1.2997 | 0.7349
[9 empty] | BCWS | ACWP |  | BCWP